## NPT_Data
ONGC Drilling NPT Intelligence Dashboard — Raw Dataset
Synthetic data generated for MDP workshop · Jan–Jun 2024 · 6 rigs · Do NOT use for operational decisions
Date | Rig Name | Well Name | Contractor | NPT Hours | Cause Category | Cause Detail | Drilling Phase | Month | Month #
2024-01-01 | Sagar Kiran | F-6-A | Baker Hughes | 17.8 | Equipment Failure | Rotary Table Failure | Drilling 12.25" | Jan-2024 | 1
2024-01-02 | Sagar Prabha | D-11-HH | Schlumberger | 14 | Equipment Failure | Hook/Block Failure | POOH (Pull Out of Hole) | Jan-2024 | 1
2024-01-02 | Sagar Ekta | G-13-B | ONGC (Own) | 3.6 | Formation/Geological | Tight Hole | Running Casing | Jan-2024 | 1
2024-01-03 | Sagar Bhushan | B-22-HH | Halliburton | 6.3 | Equipment Failure | MWD/LWD Failure | RIH (Run In Hole) | Jan-2024 | 1
2024-01-03 | Sagar Bhushan | B-22-HH | ONGC (Own) | 9.1 | Formation/Geological | Kick/Well Control Event | Drilling 12.25" | Jan-2024 | 1
2024-01-03 | Sagar Kiran | F-18-HH | ONGC (Own) | 20.5 | Formation/Geological | Wellbore Instability | Wellbore Survey | Jan-2024 | 1
2024-01-05 | Sagar Vijay | C-12-B | Schlumberger | 6 | Equipment Failure | Rotary Table Failure | Drilling 26" | Jan-2024 | 1
2024-01-05 | Sagar Vijay | C-12-B | ONGC (Own) | 11.3 | Formation/Geological | Tight Hole | Wellbore Survey | Jan-2024 | 1
2024-01-05 | Sagar Prabha | D-11-HH | ONGC (Own) | 25.3 | Weather/Environment | Cyclone Warning Stand-Down | Running BHA | Jan-2024 | 1
2024-01-05 | Sagar Sampada | E-9-HH | ONGC (Own) | 36 | Weather/Environment | Lightning Stand-Down | Completion | Jan-2024 | 1
2024-01-05 | Sagar Ekta | G-1-A | ONGC (Own) | 11.3 | Equipment Failure | BHA Failure | Running BHA | Jan-2024 | 1
2024-01-06 | Sagar Kiran | F-6-A | Schlumberger | 21.3 | Logistics/Supply | Casing Delivery Delay | Drilling 8.5" | Jan-2024 | 1
2024-01-06 | Sagar Ekta | G-13-B | ONGC (Own) | 12.3 | Logistics/Supply | Vessel Non-Availability | Drilling 26" | Jan-2024 | 1
2024-01-07 | Sagar Prabha | D-7-A | Schlumberger | 4.7 | Equipment Failure | Casing Tong Failure | POOH (Pull Out of Hole) | Jan-2024 | 1
2024-01-07 | Sagar Ekta | G-1-A | ONGC (Own) | 14.2 | Formation/Geological | Kick/Well Control Event | POOH (Pull Out of Hole) | Jan-2024 | 1
2024-01-08 | Sagar Bhushan | B-12-HH | ONGC (Own) | 10.5 | Equipment Failure | Drawworks Issue | Running Casing | Jan-2024 | 1
2024-01-08 | Sagar Vijay | C-19-A | ONGC (Own) | 29 | Well Control | Well Kill Operation | Drilling 12.25" | Jan-2024 | 1
2024-01-08 | Sagar Prabha | D-11-HH | ONGC (Own) | 21.8 | Formation/Geological | H2S Influx | POOH (Pull Out of Hole) | Jan-2024 | 1
2024-01-08 | Sagar Prabha | D-3-HH | ONGC (Own) | 7.5 | Equipment Failure | BOP Leak | Completion | Jan-2024 | 1
2024-01-08 | Sagar Sampada | E-14-B | ONGC (Own) | 2.3 | Equipment Failure | Top Drive Malfunction | Drilling 26" | Jan-2024 | 1
2024-01-08 | Sagar Ekta | G-13-B | Halliburton | 7.9 | Equipment Failure | Generator Breakdown | Drilling 26" | Jan-2024 | 1
2024-01-09 | Sagar Bhushan | B-12-HH | Schlumberger | 21.1 | Equipment Failure | Casing Tong Failure | Running BHA | Jan-2024 | 1
2024-01-09 | Sagar Ekta | G-1-A | ONGC (Own) | 13.1 | Formation/Geological | Tight Hole | Drilling 8.5" | Jan-2024 | 1
2024-01-10 | Sagar Kiran | F-6-A | ONGC (Own) | 10.4 | Formation/Geological | Wellbore Instability | Drilling 12.25" | Jan-2024 | 1
2024-01-11 | Sagar Prabha | D-11-HH | Halliburton | 12.1 | Equipment Failure | Drawworks Issue | Testing | Jan-2024 | 1
2024-01-11 | Sagar Kiran | F-6-A | ONGC (Own) | 20.9 | Formation/Geological | Lost Circulation | Cementing | Jan-2024 | 1
2024-01-11 | Sagar Kiran | F-6-A | Halliburton | 3.5 | HR/Crew | Crew Sickness | POOH (Pull Out of Hole) | Jan-2024 | 1
2024-01-11 | Sagar Kiran | F-18-HH | Schlumberger | 2.7 | HR/Crew | Competency Issue | Drilling 8.5" | Jan-2024 | 1
2024-01-12 | Sagar Kiran | F-18-HH | ONGC (Own) | 15.8 | Formation/Geological | Formation Damage | Drilling 12.25" | Jan-2024 | 1
2024-01-12 | Sagar Ekta | G-13-B | ONGC (Own) | 17.8 | Formation/Geological | Wellbore Instability | RIH (Run In Hole) | Jan-2024 | 1
2024-01-13 | Sagar Bhushan | B-12-HH | Baker Hughes | 20.6 | Equipment Failure | MWD/LWD Failure | Drilling 12.25" | Jan-2024 | 1
2024-01-13 | Sagar Bhushan | B-12-HH | ONGC (Own) | 37.7 | Well Control | Barrier Integrity Test | POOH (Pull Out of Hole) | Jan-2024 | 1
2024-01-13 | Sagar Vijay | C-19-A | ONGC (Own) | 11.7 | Formation/Geological | Tight Hole | RIH (Run In Hole) | Jan-2024 | 1
2024-01-13 | Sagar Kiran | F-6-A | Schlumberger | 4.7 | HR/Crew | Competency Issue | Completion | Jan-2024 | 1
2024-01-13 | Sagar Kiran | F-18-HH | ONGC (Own) | 7.3 | HR/Crew | Shift Handover Delay | Running BHA | Jan-2024 | 1
2024-01-13 | Sagar Ekta | G-8-HH | ONGC (Own) | 14.5 | Formation/Geological | Kick/Well Control Event | Drilling 26" | Jan-2024 | 1
2024-01-14 | Sagar Prabha | D-11-HH | Halliburton | 6.9 | HR/Crew | Competency Issue | Testing | Jan-2024 | 1
2024-01-15 | Sagar Bhushan | B-15-A | Schlumberger | 15.9 | Logistics/Supply | Cement Shortage | Drilling 8.5" | Jan-2024 | 1
2024-01-16 | Sagar Bhushan | B-12-HH | Baker Hughes | 3.3 | Equipment Failure | Casing Tong Failure | Testing | Jan-2024 | 1
2024-01-16 | Sagar Bhushan | B-12-HH | Schlumberger | 9.8 | Equipment Failure | Hook/Block Failure | RIH (Run In Hole) | Jan-2024 | 1
2024-01-17 | Sagar Kiran | F-6-A | Schlumberger | 3.2 | HR/Crew | Crew Shortage | Drilling 8.5" | Jan-2024 | 1
2024-01-18 | Sagar Bhushan | B-22-HH | Halliburton | 7.1 | Equipment Failure | Hook/Block Failure | POOH (Pull Out of Hole) | Jan-2024 | 1
2024-01-18 | Sagar Bhushan | B-12-HH | ONGC (Own) | 6.7 | Formation/Geological | Wash-Out | RIH (Run In Hole) | Jan-2024 | 1
2024-01-18 | Sagar Bhushan | B-15-A | ONGC (Own) | 53.7 | Weather/Environment | Monsoon Operations Halt | Drilling 8.5" | Jan-2024 | 1
2024-01-18 | Sagar Sampada | E-5-A | Baker Hughes | 20.1 | Well Control | Kick Observation & Shut-In | Drilling 8.5" | Jan-2024 | 1
2024-01-19 | Sagar Prabha | D-7-A | Schlumberger | 6.2 | Equipment Failure | Rotary Table Failure | Drilling 12.25" | Jan-2024 | 1
2024-01-20 | Sagar Bhushan | B-22-HH | Schlumberger | 5 | Equipment Failure | Top Drive Malfunction | Running BHA | Jan-2024 | 1
2024-01-20 | Sagar Kiran | F-18-HH | Baker Hughes | 28.4 | Well Control | Well Kill Operation | RIH (Run In Hole) | Jan-2024 | 1
2024-01-20 | Sagar Kiran | F-2-HH | Baker Hughes | 5.7 | HR/Crew | Crew Shortage | Testing | Jan-2024 | 1
2024-01-22 | Sagar Bhushan | B-22-HH | Halliburton | 12.3 | Equipment Failure | Generator Breakdown | Drilling 12.25" | Jan-2024 | 1
2024-01-22 | Sagar Vijay | C-12-B | Halliburton | 4.6 | Equipment Failure | Generator Breakdown | Cementing | Jan-2024 | 1
2024-01-22 | Sagar Sampada | E-9-HH | ONGC (Own) | 8.1 | Formation/Geological | Tight Hole | Drilling 12.25" | Jan-2024 | 1
2024-01-22 | Sagar Sampada | E-9-HH | ONGC (Own) | 36.4 | Weather/Environment | Heavy Swell (>3m) | POOH (Pull Out of Hole) | Jan-2024 | 1
2024-01-22 | Sagar Kiran | F-18-HH | Baker Hughes | 1.8 | HR/Crew | Competency Issue | Drilling 12.25" | Jan-2024 | 1
2024-01-22 | Sagar Kiran | F-2-HH | ONGC (Own) | 20.1 | Formation/Geological | H2S Influx | Testing | Jan-2024 | 1
2024-01-23 | Sagar Bhushan | B-22-HH | Halliburton | 6.2 | Equipment Failure | Top Drive Malfunction | Running Casing | Jan-2024 | 1
2024-01-23 | Sagar Bhushan | B-12-HH | ONGC (Own) | 40.7 | Weather/Environment | Heavy Swell (>3m) | Drilling 8.5" | Jan-2024 | 1
2024-01-23 | Sagar Bhushan | B-22-HH | Baker Hughes | 12.7 | Equipment Failure | Top Drive Malfunction | Running Casing | Jan-2024 | 1
2024-01-23 | Sagar Bhushan | B-22-HH | ONGC (Own) | 12.5 | Formation/Geological | Wellbore Instability | Cementing | Jan-2024 | 1
2024-01-23 | Sagar Bhushan | B-22-HH | Schlumberger | 10.2 | Equipment Failure | Hook/Block Failure | Running Casing | Jan-2024 | 1
2024-01-23 | Sagar Vijay | C-8-HH | ONGC (Own) | 37.6 | Weather/Environment | Heavy Swell (>3m) | Testing | Jan-2024 | 1
2024-01-23 | Sagar Prabha | D-3-HH | ONGC (Own) | 65.3 | Weather/Environment | Low Visibility/Fog | Wellbore Survey | Jan-2024 | 1
2024-01-23 | Sagar Prabha | D-3-HH | Baker Hughes | 11.5 | Equipment Failure | Rotary Table Failure | Testing | Jan-2024 | 1
2024-01-23 | Sagar Prabha | D-11-HH | ONGC (Own) | 44.6 | Weather/Environment | High Wind Speed (>25 knots) | Drilling 12.25" | Jan-2024 | 1
2024-01-23 | Sagar Kiran | F-18-HH | ONGC (Own) | 12.1 | Formation/Geological | Tight Hole | RIH (Run In Hole) | Jan-2024 | 1
2024-01-23 | Sagar Ekta | G-1-A | ONGC (Own) | 4.9 | Equipment Failure | BHA Failure | Completion | Jan-2024 | 1
2024-01-24 | Sagar Ekta | G-1-A | ONGC (Own) | 17.9 | Formation/Geological | Lost Circulation | Cementing | Jan-2024 | 1
2024-01-26 | Sagar Vijay | C-8-HH | ONGC (Own) | 14.6 | Formation/Geological | Tight Hole | POOH (Pull Out of Hole) | Jan-2024 | 1
2024-01-26 | Sagar Vijay | C-8-HH | Halliburton | 8.7 | Logistics/Supply | Cement Shortage | Completion | Jan-2024 | 1
2024-01-26 | Sagar Vijay | C-19-A | ONGC (Own) | 3.5 | Equipment Failure | Rotary Table Failure | Testing | Jan-2024 | 1
2024-01-26 | Sagar Prabha | D-3-HH | ONGC (Own) | 18.1 | Formation/Geological | Kick/Well Control Event | Running Casing | Jan-2024 | 1
2024-01-26 | Sagar Kiran | F-18-HH | Halliburton | 6.4 | HR/Crew | HSE Training Stand-Down | Drilling 12.25" | Jan-2024 | 1
2024-01-26 | Sagar Ekta | G-1-A | Schlumberger | 21.4 | Logistics/Supply | Completion Equipment Delay | RIH (Run In Hole) | Jan-2024 | 1
2024-01-27 | Sagar Bhushan | B-12-HH | Baker Hughes | 6.3 | Equipment Failure | BOP Leak | Running Casing | Jan-2024 | 1
2024-01-27 | Sagar Prabha | D-11-HH | Halliburton | 6.4 | Equipment Failure | Top Drive Malfunction | RIH (Run In Hole) | Jan-2024 | 1
2024-01-27 | Sagar Ekta | G-8-HH | Baker Hughes | 1.1 | HR/Crew | HSE Training Stand-Down | Cementing | Jan-2024 | 1
2024-01-28 | Sagar Bhushan | B-22-HH | Schlumberger | 20.9 | Equipment Failure | Casing Tong Failure | Drilling 12.25" | Jan-2024 | 1
2024-01-28 | Sagar Kiran | F-6-A | Halliburton | 2.4 | HR/Crew | HSE Training Stand-Down | Testing | Jan-2024 | 1
2024-01-28 | Sagar Ekta | G-13-B | ONGC (Own) | 3 | Equipment Failure | Top Drive Malfunction | Completion | Jan-2024 | 1
2024-01-29 | Sagar Prabha | D-7-A | Halliburton | 4.7 | Logistics/Supply | Chemical Supply Delay | POOH (Pull Out of Hole) | Jan-2024 | 1
2024-01-29 | Sagar Ekta | G-8-HH | Halliburton | 12.9 | Equipment Failure | Top Drive Malfunction | RIH (Run In Hole) | Jan-2024 | 1
2024-01-30 | Sagar Bhushan | B-12-HH | Baker Hughes | 35.8 | Well Control | BOP Test Failure | Drilling 12.25" | Jan-2024 | 1
2024-01-30 | Sagar Vijay | C-8-HH | ONGC (Own) | 14.6 | Formation/Geological | Lost Circulation | RIH (Run In Hole) | Jan-2024 | 1
2024-01-30 | Sagar Prabha | D-7-A | Schlumberger | 16.7 | Equipment Failure | Generator Breakdown | Completion | Jan-2024 | 1
2024-01-30 | Sagar Prabha | D-7-A | ONGC (Own) | 21.4 | Formation/Geological | Lost Circulation | Completion | Jan-2024 | 1
2024-01-30 | Sagar Prabha | D-3-HH | Schlumberger | 13.7 | Equipment Failure | Drawworks Issue | Cementing | Jan-2024 | 1
2024-01-31 | Sagar Bhushan | B-22-HH | ONGC (Own) | 66.6 | Weather/Environment | Monsoon Operations Halt | POOH (Pull Out of Hole) | Jan-2024 | 1
2024-01-31 | Sagar Prabha | D-7-A | Schlumberger | 15.4 | Equipment Failure | Generator Breakdown | Testing | Jan-2024 | 1
2024-01-31 | Sagar Sampada | E-14-B | ONGC (Own) | 3.5 | Third Party/Regulatory | Third Party Certification | Testing | Jan-2024 | 1
2024-02-02 | Sagar Bhushan | B-12-HH | Halliburton | 13 | Equipment Failure | MWD/LWD Failure | Testing | Feb-2024 | 2
2024-02-02 | Sagar Bhushan | B-22-HH | Schlumberger | 4.2 | Equipment Failure | Rotary Table Failure | Wellbore Survey | Feb-2024 | 2
2024-02-02 | Sagar Vijay | C-19-A | Halliburton | 4.6 | HR/Crew | Competency Issue | Testing | Feb-2024 | 2
2024-02-03 | Sagar Prabha | D-11-HH | ONGC (Own) | 15.4 | Formation/Geological | Wellbore Instability | Completion | Feb-2024 | 2
2024-02-03 | Sagar Prabha | D-11-HH | ONGC (Own) | 20.3 | Weather/Environment | Monsoon Operations Halt | Running BHA | Feb-2024 | 2
2024-02-05 | Sagar Ekta | G-8-HH | ONGC (Own) | 25.4 | Logistics/Supply | Cement Shortage | Running Casing | Feb-2024 | 2
2024-02-06 | Sagar Bhushan | B-12-HH | Halliburton | 1.4 | HR/Crew | Crew Change Delay | Running Casing | Feb-2024 | 2
2024-02-07 | Sagar Bhushan | B-15-A | Schlumberger | 12.8 | Equipment Failure | Hook/Block Failure | Running BHA | Feb-2024 | 2
2024-02-07 | Sagar Bhushan | B-12-HH | ONGC (Own) | 35.7 | Weather/Environment | High Wind Speed (>25 knots) | Running Casing | Feb-2024 | 2
2024-02-08 | Sagar Sampada | E-14-B | ONGC (Own) | 5.6 | Formation/Geological | Formation Damage | RIH (Run In Hole) | Feb-2024 | 2
2024-02-09 | Sagar Vijay | C-19-A | ONGC (Own) | 13 | Formation/Geological | Wellbore Instability | RIH (Run In Hole) | Feb-2024 | 2
2024-02-09 | Sagar Prabha | D-3-HH | Halliburton | 8.4 | Equipment Failure | Generator Breakdown | Drilling 26" | Feb-2024 | 2
2024-02-09 | Sagar Kiran | F-18-HH | Halliburton | 10.6 | Equipment Failure | Generator Breakdown | Drilling 12.25" | Feb-2024 | 2
2024-02-09 | Sagar Ekta | G-13-B | Schlumberger | 11.7 | Equipment Failure | MWD/LWD Failure | Running Casing | Feb-2024 | 2
2024-02-09 | Sagar Ekta | G-13-B | Schlumberger | 21.8 | Logistics/Supply | Vessel Non-Availability | Testing | Feb-2024 | 2
2024-02-10 | Sagar Bhushan | B-12-HH | ONGC (Own) | 7.3 | Equipment Failure | Generator Breakdown | Running Casing | Feb-2024 | 2
2024-02-10 | Sagar Prabha | D-7-A | Halliburton | 9.5 | Equipment Failure | Hook/Block Failure | Running Casing | Feb-2024 | 2
2024-02-10 | Sagar Sampada | E-5-A | ONGC (Own) | 10.9 | Weather/Environment | Lightning Stand-Down | Running Casing | Feb-2024 | 2
2024-02-10 | Sagar Kiran | F-2-HH | Baker Hughes | 6.6 | Equipment Failure | MWD/LWD Failure | RIH (Run In Hole) | Feb-2024 | 2
2024-02-10 | Sagar Kiran | F-6-A | Schlumberger | 11.4 | Equipment Failure | Casing Tong Failure | Cementing | Feb-2024 | 2
2024-02-11 | Sagar Vijay | C-8-HH | Schlumberger | 5.6 | Equipment Failure | Hook/Block Failure | Cementing | Feb-2024 | 2
2024-02-11 | Sagar Prabha | D-3-HH | ONGC (Own) | 13.2 | Formation/Geological | Wellbore Instability | Drilling 12.25" | Feb-2024 | 2
2024-02-11 | Sagar Sampada | E-5-A | ONGC (Own) | 4.5 | Formation/Geological | Stuck Pipe | Wellbore Survey | Feb-2024 | 2
2024-02-11 | Sagar Ekta | G-8-HH | Schlumberger | 13.8 | Logistics/Supply | Drill Bit Delivery Delay | Testing | Feb-2024 | 2
2024-02-12 | Sagar Prabha | D-3-HH | Baker Hughes | 12.5 | Equipment Failure | Hook/Block Failure | Drilling 26" | Feb-2024 | 2
2024-02-12 | Sagar Kiran | F-6-A | Halliburton | 6.7 | Equipment Failure | MWD/LWD Failure | Cementing | Feb-2024 | 2
2024-02-13 | Sagar Bhushan | B-15-A | ONGC (Own) | 25.2 | Formation/Geological | Tight Hole | Drilling 26" | Feb-2024 | 2
2024-02-13 | Sagar Vijay | C-8-HH | ONGC (Own) | 11.8 | Equipment Failure | MWD/LWD Failure | Running Casing | Feb-2024 | 2
2024-02-13 | Sagar Vijay | C-19-A | Schlumberger | 9.4 | Equipment Failure | Pump Breakdown | Testing | Feb-2024 | 2
2024-02-13 | Sagar Sampada | E-5-A | Halliburton | 7 | Equipment Failure | Generator Breakdown | Drilling 26" | Feb-2024 | 2
2024-02-13 | Sagar Kiran | F-2-HH | ONGC (Own) | 20.7 | Weather/Environment | Heavy Swell (>3m) | Testing | Feb-2024 | 2
2024-02-14 | Sagar Sampada | E-14-B | ONGC (Own) | 39.4 | Weather/Environment | Monsoon Operations Halt | Testing | Feb-2024 | 2
2024-02-15 | Sagar Bhushan | B-12-HH | ONGC (Own) | 5.4 | Equipment Failure | Rotary Table Failure | Drilling 12.25" | Feb-2024 | 2
2024-02-15 | Sagar Kiran | F-18-HH | Baker Hughes | 4.5 | HR/Crew | Crew Sickness | Completion | Feb-2024 | 2
2024-02-16 | Sagar Bhushan | B-15-A | Schlumberger | 3.3 | Equipment Failure | Drawworks Issue | Testing | Feb-2024 | 2
2024-02-16 | Sagar Prabha | D-7-A | ONGC (Own) | 19.7 | Formation/Geological | Wash-Out | Drilling 8.5" | Feb-2024 | 2
2024-02-16 | Sagar Kiran | F-6-A | ONGC (Own) | 11.4 | Formation/Geological | Wash-Out | POOH (Pull Out of Hole) | Feb-2024 | 2
2024-02-17 | Sagar Sampada | E-9-HH | ONGC (Own) | 38.1 | Weather/Environment | Lightning Stand-Down | RIH (Run In Hole) | Feb-2024 | 2
2024-02-18 | Sagar Vijay | C-8-HH | Baker Hughes | 6.5 | Well Control | Flow Check | Cementing | Feb-2024 | 2
2024-02-18 | Sagar Prabha | D-7-A | Halliburton | 8.5 | Equipment Failure | Hook/Block Failure | Wellbore Survey | Feb-2024 | 2
2024-02-18 | Sagar Kiran | F-18-HH | Halliburton | 4.7 | HR/Crew | HSE Training Stand-Down | POOH (Pull Out of Hole) | Feb-2024 | 2
2024-02-19 | Sagar Bhushan | B-12-HH | Baker Hughes | 3.1 | Equipment Failure | BOP Leak | Drilling 26" | Feb-2024 | 2
2024-02-19 | Sagar Vijay | C-12-B | ONGC (Own) | 3.3 | Formation/Geological | Kick/Well Control Event | Drilling 26" | Feb-2024 | 2
2024-02-20 | Sagar Bhushan | B-12-HH | ONGC (Own) | 4.4 | Formation/Geological | Wellbore Instability | Drilling 12.25" | Feb-2024 | 2
2024-02-20 | Sagar Prabha | D-7-A | Baker Hughes | 12.2 | Equipment Failure | MWD/LWD Failure | Drilling 26" | Feb-2024 | 2
2024-02-20 | Sagar Ekta | G-13-B | ONGC (Own) | 4.4 | Weather/Environment | Cyclone Warning Stand-Down | Drilling 8.5" | Feb-2024 | 2
2024-02-20 | Sagar Ekta | G-13-B | ONGC (Own) | 3.1 | Formation/Geological | Lost Circulation | Testing | Feb-2024 | 2
2024-02-21 | Sagar Prabha | D-7-A | Baker Hughes | 25.8 | Well Control | Barrier Integrity Test | Drilling 26" | Feb-2024 | 2
2024-02-21 | Sagar Prabha | D-11-HH | ONGC (Own) | 18.5 | Formation/Geological | Wellbore Instability | POOH (Pull Out of Hole) | Feb-2024 | 2
2024-02-21 | Sagar Kiran | F-6-A | ONGC (Own) | 15.9 | Formation/Geological | Kick/Well Control Event | Drilling 12.25" | Feb-2024 | 2
2024-02-21 | Sagar Kiran | F-18-HH | Halliburton | 7 | HR/Crew | Crew Change Delay | POOH (Pull Out of Hole) | Feb-2024 | 2
2024-02-22 | Sagar Bhushan | B-22-HH | ONGC (Own) | 9.9 | Equipment Failure | Drawworks Issue | Drilling 26" | Feb-2024 | 2
2024-02-22 | Sagar Vijay | C-19-A | Schlumberger | 1.9 | HR/Crew | HSE Training Stand-Down | Cementing | Feb-2024 | 2
2024-02-22 | Sagar Ekta | G-8-HH | ONGC (Own) | 9.8 | Formation/Geological | Formation Damage | Cementing | Feb-2024 | 2
2024-02-23 | Sagar Vijay | C-19-A | Baker Hughes | 11.7 | Equipment Failure | Drawworks Issue | Running BHA | Feb-2024 | 2
2024-02-23 | Sagar Sampada | E-14-B | ONGC (Own) | 39.1 | Weather/Environment | Low Visibility/Fog | Completion | Feb-2024 | 2
2024-02-23 | Sagar Kiran | F-2-HH | Schlumberger | 6.3 | HR/Crew | Crew Change Delay | Wellbore Survey | Feb-2024 | 2
2024-02-24 | Sagar Prabha | D-7-A | ONGC (Own) | 9.7 | Formation/Geological | Stuck Pipe | Running Casing | Feb-2024 | 2
2024-02-25 | Sagar Vijay | C-12-B | ONGC (Own) | 21.7 | Logistics/Supply | Drill Bit Delivery Delay | Cementing | Feb-2024 | 2
2024-02-25 | Sagar Prabha | D-7-A | ONGC (Own) | 7.7 | Equipment Failure | BOP Leak | Drilling 26" | Feb-2024 | 2
2024-02-26 | Sagar Vijay | C-19-A | ONGC (Own) | 15.3 | Formation/Geological | Wash-Out | Completion | Feb-2024 | 2
2024-02-26 | Sagar Prabha | D-7-A | Baker Hughes | 14.3 | Equipment Failure | BHA Failure | Drilling 12.25" | Feb-2024 | 2
2024-02-26 | Sagar Kiran | F-2-HH | ONGC (Own) | 6.4 | Formation/Geological | Tight Hole | Running Casing | Feb-2024 | 2
2024-02-27 | Sagar Kiran | F-2-HH | Schlumberger | 33.8 | Logistics/Supply | Chemical Supply Delay | Running Casing | Feb-2024 | 2
2024-02-28 | Sagar Kiran | F-2-HH | ONGC (Own) | 5.8 | Formation/Geological | Lost Circulation | Cementing | Feb-2024 | 2
2024-02-29 | Sagar Prabha | D-3-HH | Schlumberger | 2.5 | Equipment Failure | Generator Breakdown | Running Casing | Feb-2024 | 2
2024-03-01 | Sagar Prabha | D-3-HH | Baker Hughes | 8.3 | Equipment Failure | Drawworks Issue | Drilling 12.25" | Mar-2024 | 3
2024-03-01 | Sagar Prabha | D-3-HH | Schlumberger | 7.8 | HR/Crew | Crew Change Delay | POOH (Pull Out of Hole) | Mar-2024 | 3
2024-03-01 | Sagar Kiran | F-6-A | Schlumberger | 1.1 | HR/Crew | Crew Sickness | POOH (Pull Out of Hole) | Mar-2024 | 3
2024-03-01 | Sagar Kiran | F-18-HH | Halliburton | 9.5 | Equipment Failure | MWD/LWD Failure | Drilling 12.25" | Mar-2024 | 3
2024-03-02 | Sagar Prabha | D-7-A | ONGC (Own) | 4.6 | Equipment Failure | Rotary Table Failure | POOH (Pull Out of Hole) | Mar-2024 | 3
2024-03-03 | Sagar Prabha | D-11-HH | ONGC (Own) | 71.2 | Weather/Environment | Monsoon Operations Halt | Drilling 26" | Mar-2024 | 3
2024-03-03 | Sagar Prabha | D-11-HH | ONGC (Own) | 19.7 | Formation/Geological | Wash-Out | Drilling 12.25" | Mar-2024 | 3
2024-03-03 | Sagar Kiran | F-2-HH | ONGC (Own) | 11.6 | Third Party/Regulatory | Environmental Audit | Cementing | Mar-2024 | 3
2024-03-04 | Sagar Vijay | C-12-B | ONGC (Own) | 24.1 | Weather/Environment | Monsoon Operations Halt | Testing | Mar-2024 | 3
2024-03-04 | Sagar Ekta | G-8-HH | Baker Hughes | 10.7 | Equipment Failure | MWD/LWD Failure | Drilling 8.5" | Mar-2024 | 3
2024-03-05 | Sagar Bhushan | B-22-HH | Halliburton | 7.5 | Equipment Failure | Pump Breakdown | RIH (Run In Hole) | Mar-2024 | 3
2024-03-05 | Sagar Bhushan | B-22-HH | Baker Hughes | 13.3 | Equipment Failure | Pump Breakdown | RIH (Run In Hole) | Mar-2024 | 3
2024-03-05 | Sagar Prabha | D-3-HH | ONGC (Own) | 17.4 | Formation/Geological | Kick/Well Control Event | Drilling 12.25" | Mar-2024 | 3
2024-03-05 | Sagar Prabha | D-11-HH | ONGC (Own) | 10.3 | Equipment Failure | Generator Breakdown | Drilling 12.25" | Mar-2024 | 3
2024-03-05 | Sagar Prabha | D-3-HH | ONGC (Own) | 33.1 | Weather/Environment | Heavy Swell (>3m) | RIH (Run In Hole) | Mar-2024 | 3
2024-03-06 | Sagar Bhushan | B-15-A | Schlumberger | 20.2 | Equipment Failure | Drawworks Issue | Cementing | Mar-2024 | 3
2024-03-06 | Sagar Prabha | D-3-HH | Baker Hughes | 6.6 | Equipment Failure | BOP Leak | Testing | Mar-2024 | 3
2024-03-06 | Sagar Prabha | D-11-HH | ONGC (Own) | 46.1 | Weather/Environment | Heavy Swell (>3m) | Testing | Mar-2024 | 3
2024-03-06 | Sagar Ekta | G-13-B | ONGC (Own) | 11.3 | Formation/Geological | Formation Damage | RIH (Run In Hole) | Mar-2024 | 3
2024-03-07 | Sagar Bhushan | B-12-HH | Halliburton | 14.8 | Equipment Failure | Generator Breakdown | RIH (Run In Hole) | Mar-2024 | 3
2024-03-07 | Sagar Prabha | D-3-HH | Baker Hughes | 7.5 | Equipment Failure | MWD/LWD Failure | Cementing | Mar-2024 | 3
2024-03-07 | Sagar Ekta | G-1-A | Halliburton | 5.8 | Equipment Failure | BOP Leak | Drilling 8.5" | Mar-2024 | 3
2024-03-08 | Sagar Vijay | C-8-HH | ONGC (Own) | 11.3 | Formation/Geological | Kick/Well Control Event | Testing | Mar-2024 | 3
2024-03-09 | Sagar Bhushan | B-22-HH | Baker Hughes | 6.2 | Equipment Failure | Drawworks Issue | POOH (Pull Out of Hole) | Mar-2024 | 3
2024-03-09 | Sagar Kiran | F-2-HH | ONGC (Own) | 33.3 | Weather/Environment | Monsoon Operations Halt | POOH (Pull Out of Hole) | Mar-2024 | 3
2024-03-10 | Sagar Bhushan | B-22-HH | ONGC (Own) | 19.7 | Formation/Geological | Kick/Well Control Event | RIH (Run In Hole) | Mar-2024 | 3
2024-03-10 | Sagar Kiran | F-2-HH | ONGC (Own) | 21.1 | Logistics/Supply | Casing Delivery Delay | Running BHA | Mar-2024 | 3
2024-03-11 | Sagar Bhushan | B-12-HH | Schlumberger | 29.5 | Logistics/Supply | Drill Bit Delivery Delay | Drilling 26" | Mar-2024 | 3
2024-03-11 | Sagar Sampada | E-5-A | Baker Hughes | 9.1 | Equipment Failure | Generator Breakdown | Completion | Mar-2024 | 3
2024-03-11 | Sagar Kiran | F-2-HH | Schlumberger | 1.6 | HR/Crew | HSE Training Stand-Down | RIH (Run In Hole) | Mar-2024 | 3
2024-03-11 | Sagar Ekta | G-1-A | ONGC (Own) | 5.4 | Formation/Geological | Wash-Out | POOH (Pull Out of Hole) | Mar-2024 | 3
2024-03-12 | Sagar Vijay | C-12-B | Schlumberger | 3.1 | Equipment Failure | Top Drive Malfunction | POOH (Pull Out of Hole) | Mar-2024 | 3
2024-03-12 | Sagar Vijay | C-19-A | Baker Hughes | 34 | Well Control | BOP Test Failure | Testing | Mar-2024 | 3
2024-03-12 | Sagar Prabha | D-11-HH | ONGC (Own) | 12.5 | Weather/Environment | High Wind Speed (>25 knots) | Completion | Mar-2024 | 3
2024-03-13 | Sagar Kiran | F-2-HH | ONGC (Own) | 6.3 | HR/Crew | Crew Sickness | Running Casing | Mar-2024 | 3
2024-03-14 | Sagar Bhushan | B-22-HH | Baker Hughes | 14.3 | Equipment Failure | Top Drive Malfunction | Completion | Mar-2024 | 3
2024-03-14 | Sagar Ekta | G-1-A | Halliburton | 3.7 | HR/Crew | Crew Shortage | Wellbore Survey | Mar-2024 | 3
2024-03-15 | Sagar Vijay | C-8-HH | Baker Hughes | 1.2 | HR/Crew | HSE Training Stand-Down | POOH (Pull Out of Hole) | Mar-2024 | 3
2024-03-15 | Sagar Sampada | E-14-B | Baker Hughes | 4.9 | Equipment Failure | Drawworks Issue | POOH (Pull Out of Hole) | Mar-2024 | 3
2024-03-17 | Sagar Bhushan | B-15-A | Baker Hughes | 22 | Equipment Failure | Top Drive Malfunction | Testing | Mar-2024 | 3
2024-03-17 | Sagar Ekta | G-8-HH | Halliburton | 2.7 | Equipment Failure | Generator Breakdown | Running Casing | Mar-2024 | 3
2024-03-18 | Sagar Bhushan | B-22-HH | ONGC (Own) | 2.5 | HR/Crew | HSE Training Stand-Down | Running BHA | Mar-2024 | 3
2024-03-18 | Sagar Sampada | E-9-HH | ONGC (Own) | 30.7 | Weather/Environment | Low Visibility/Fog | Drilling 12.25" | Mar-2024 | 3
2024-03-18 | Sagar Kiran | F-18-HH | ONGC (Own) | 55.8 | Weather/Environment | Lightning Stand-Down | RIH (Run In Hole) | Mar-2024 | 3
2024-03-19 | Sagar Bhushan | B-15-A | ONGC (Own) | 28.6 | Formation/Geological | Formation Damage | Drilling 8.5" | Mar-2024 | 3
2024-03-19 | Sagar Kiran | F-2-HH | Schlumberger | 8.6 | HR/Crew | Competency Issue | RIH (Run In Hole) | Mar-2024 | 3
2024-03-19 | Sagar Kiran | F-2-HH | ONGC (Own) | 5 | Formation/Geological | H2S Influx | Drilling 12.25" | Mar-2024 | 3
2024-03-19 | Sagar Kiran | F-2-HH | ONGC (Own) | 6.2 | HR/Crew | Shift Handover Delay | Drilling 26" | Mar-2024 | 3
2024-03-19 | Sagar Ekta | G-8-HH | Baker Hughes | 7.3 | Equipment Failure | Casing Tong Failure | Cementing | Mar-2024 | 3
2024-03-20 | Sagar Bhushan | B-22-HH | ONGC (Own) | 12.9 | Formation/Geological | H2S Influx | Completion | Mar-2024 | 3
2024-03-20 | Sagar Bhushan | B-22-HH | ONGC (Own) | 15.8 | Equipment Failure | Rotary Table Failure | Drilling 8.5" | Mar-2024 | 3
2024-03-20 | Sagar Bhushan | B-15-A | ONGC (Own) | 11.3 | Formation/Geological | Stuck Pipe | Wellbore Survey | Mar-2024 | 3
2024-03-20 | Sagar Prabha | D-11-HH | Schlumberger | 6.2 | Equipment Failure | Hook/Block Failure | Running BHA | Mar-2024 | 3
2024-03-21 | Sagar Vijay | C-19-A | ONGC (Own) | 16.1 | Formation/Geological | Formation Damage | Drilling 12.25" | Mar-2024 | 3
2024-03-21 | Sagar Prabha | D-3-HH | ONGC (Own) | 6.1 | Third Party/Regulatory | Coast Guard Inspection | RIH (Run In Hole) | Mar-2024 | 3
2024-03-21 | Sagar Kiran | F-2-HH | Schlumberger | 6.1 | HR/Crew | HSE Training Stand-Down | Running BHA | Mar-2024 | 3
2024-03-21 | Sagar Kiran | F-2-HH | ONGC (Own) | 27.2 | Weather/Environment | Lightning Stand-Down | Cementing | Mar-2024 | 3
2024-03-21 | Sagar Kiran | F-2-HH | ONGC (Own) | 40.5 | Weather/Environment | Heavy Swell (>3m) | POOH (Pull Out of Hole) | Mar-2024 | 3
2024-03-21 | Sagar Kiran | F-18-HH | ONGC (Own) | 8 | HR/Crew | Crew Change Delay | Cementing | Mar-2024 | 3
2024-03-21 | Sagar Ekta | G-13-B | Schlumberger | 11.1 | Equipment Failure | Casing Tong Failure | Completion | Mar-2024 | 3
2024-03-22 | Sagar Bhushan | B-15-A | Halliburton | 20.6 | Equipment Failure | Drawworks Issue | Running Casing | Mar-2024 | 3
2024-03-22 | Sagar Bhushan | B-12-HH | Schlumberger | 9.2 | Equipment Failure | Generator Breakdown | Drilling 26" | Mar-2024 | 3
2024-03-22 | Sagar Prabha | D-11-HH | Halliburton | 17 | Logistics/Supply | Cement Shortage | Completion | Mar-2024 | 3
2024-03-22 | Sagar Ekta | G-13-B | Baker Hughes | 12.3 | Equipment Failure | Hook/Block Failure | Running Casing | Mar-2024 | 3
2024-03-22 | Sagar Ekta | G-1-A | ONGC (Own) | 22.6 | Logistics/Supply | Chemical Supply Delay | Drilling 26" | Mar-2024 | 3
2024-03-23 | Sagar Bhushan | B-12-HH | Baker Hughes | 12.8 | Equipment Failure | Hook/Block Failure | Testing | Mar-2024 | 3
2024-03-23 | Sagar Bhushan | B-15-A | ONGC (Own) | 82 | Weather/Environment | Lightning Stand-Down | Drilling 26" | Mar-2024 | 3
2024-03-23 | Sagar Bhushan | B-15-A | ONGC (Own) | 12.5 | Equipment Failure | Casing Tong Failure | Running BHA | Mar-2024 | 3
2024-03-23 | Sagar Prabha | D-7-A | ONGC (Own) | 65.5 | Weather/Environment | Lightning Stand-Down | Cementing | Mar-2024 | 3
2024-03-23 | Sagar Kiran | F-2-HH | ONGC (Own) | 2.7 | HR/Crew | Shift Handover Delay | Drilling 26" | Mar-2024 | 3
2024-03-24 | Sagar Ekta | G-13-B | Baker Hughes | 3.2 | HR/Crew | Shift Handover Delay | Drilling 8.5" | Mar-2024 | 3
2024-03-24 | Sagar Ekta | G-8-HH | ONGC (Own) | 5.3 | Equipment Failure | Casing Tong Failure | Running BHA | Mar-2024 | 3
2024-03-24 | Sagar Ekta | G-13-B | ONGC (Own) | 24.8 | Weather/Environment | Lightning Stand-Down | Running Casing | Mar-2024 | 3
2024-03-25 | Sagar Prabha | D-7-A | ONGC (Own) | 17.1 | Formation/Geological | Wellbore Instability | POOH (Pull Out of Hole) | Mar-2024 | 3
2024-03-25 | Sagar Sampada | E-14-B | Schlumberger | 5.7 | Equipment Failure | MWD/LWD Failure | Completion | Mar-2024 | 3
2024-03-25 | Sagar Kiran | F-6-A | ONGC (Own) | 5.4 | HR/Crew | Shift Handover Delay | Testing | Mar-2024 | 3
2024-03-25 | Sagar Kiran | F-2-HH | Baker Hughes | 7.5 | Equipment Failure | Top Drive Malfunction | Running BHA | Mar-2024 | 3
2024-03-25 | Sagar Ekta | G-8-HH | Schlumberger | 3.6 | Logistics/Supply | Cement Shortage | Running Casing | Mar-2024 | 3
2024-03-26 | Sagar Bhushan | B-12-HH | ONGC (Own) | 53.8 | Well Control | Kick Observation & Shut-In | Completion | Mar-2024 | 3
2024-03-26 | Sagar Sampada | E-5-A | ONGC (Own) | 19.6 | Weather/Environment | Low Visibility/Fog | Running Casing | Mar-2024 | 3
2024-03-27 | Sagar Prabha | D-11-HH | ONGC (Own) | 48.3 | Weather/Environment | Heavy Swell (>3m) | Drilling 26" | Mar-2024 | 3
2024-03-28 | Sagar Bhushan | B-15-A | ONGC (Own) | 19.1 | Well Control | Kick Observation & Shut-In | Drilling 26" | Mar-2024 | 3
2024-03-28 | Sagar Prabha | D-3-HH | ONGC (Own) | 57.9 | Weather/Environment | Monsoon Operations Halt | Drilling 8.5" | Mar-2024 | 3
2024-03-28 | Sagar Kiran | F-18-HH | Baker Hughes | 14.6 | Equipment Failure | Hook/Block Failure | Drilling 26" | Mar-2024 | 3
2024-03-28 | Sagar Kiran | F-2-HH | ONGC (Own) | 76.8 | Weather/Environment | High Wind Speed (>25 knots) | Running BHA | Mar-2024 | 3
2024-03-30 | Sagar Bhushan | B-15-A | Baker Hughes | 15.9 | Equipment Failure | Pump Breakdown | Completion | Mar-2024 | 3
2024-03-30 | Sagar Bhushan | B-22-HH | ONGC (Own) | 20.3 | Equipment Failure | BOP Leak | Drilling 8.5" | Mar-2024 | 3
2024-03-30 | Sagar Sampada | E-14-B | ONGC (Own) | 43.8 | Weather/Environment | Heavy Swell (>3m) | POOH (Pull Out of Hole) | Mar-2024 | 3
2024-03-30 | Sagar Kiran | F-18-HH | Schlumberger | 8.1 | Equipment Failure | Generator Breakdown | Drilling 8.5" | Mar-2024 | 3
2024-03-31 | Sagar Vijay | C-8-HH | Halliburton | 4.1 | HR/Crew | HSE Training Stand-Down | Drilling 26" | Mar-2024 | 3
2024-03-31 | Sagar Sampada | E-9-HH | Schlumberger | 1.9 | HR/Crew | Shift Handover Delay | Cementing | Mar-2024 | 3
2024-04-01 | Sagar Vijay | C-19-A | ONGC (Own) | 15 | Formation/Geological | Formation Damage | Completion | Apr-2024 | 4
2024-04-02 | Sagar Ekta | G-13-B | Halliburton | 6.8 | HR/Crew | Shift Handover Delay | Drilling 26" | Apr-2024 | 4
2024-04-04 | Sagar Kiran | F-18-HH | Halliburton | 3.6 | HR/Crew | Competency Issue | Completion | Apr-2024 | 4
2024-04-04 | Sagar Kiran | F-2-HH | ONGC (Own) | 19.9 | Logistics/Supply | Chemical Supply Delay | Wellbore Survey | Apr-2024 | 4
2024-04-04 | Sagar Ekta | G-13-B | ONGC (Own) | 51.8 | Weather/Environment | Lightning Stand-Down | Wellbore Survey | Apr-2024 | 4
2024-04-05 | Sagar Bhushan | B-22-HH | Halliburton | 16.5 | Equipment Failure | Hook/Block Failure | Running BHA | Apr-2024 | 4
2024-04-05 | Sagar Prabha | D-11-HH | ONGC (Own) | 14 | Equipment Failure | Pump Breakdown | POOH (Pull Out of Hole) | Apr-2024 | 4
2024-04-05 | Sagar Kiran | F-2-HH | Baker Hughes | 8.7 | HR/Crew | Crew Sickness | Completion | Apr-2024 | 4
2024-04-05 | Sagar Ekta | G-13-B | ONGC (Own) | 28.1 | Logistics/Supply | Drill Bit Delivery Delay | POOH (Pull Out of Hole) | Apr-2024 | 4
2024-04-07 | Sagar Bhushan | B-15-A | ONGC (Own) | 10.9 | Equipment Failure | Rotary Table Failure | Drilling 26" | Apr-2024 | 4
2024-04-07 | Sagar Vijay | C-8-HH | ONGC (Own) | 17.5 | Formation/Geological | Lost Circulation | Testing | Apr-2024 | 4
2024-04-07 | Sagar Sampada | E-9-HH | ONGC (Own) | 2.2 | Equipment Failure | Pump Breakdown | Drilling 8.5" | Apr-2024 | 4
2024-04-07 | Sagar Kiran | F-2-HH | ONGC (Own) | 3.7 | HR/Crew | HSE Training Stand-Down | Completion | Apr-2024 | 4
2024-04-07 | Sagar Ekta | G-13-B | Halliburton | 2.6 | Logistics/Supply | Completion Equipment Delay | Drilling 8.5" | Apr-2024 | 4
2024-04-07 | Sagar Ekta | G-8-HH | ONGC (Own) | 11.1 | Weather/Environment | Lightning Stand-Down | Drilling 8.5" | Apr-2024 | 4
2024-04-07 | Sagar Ekta | G-8-HH | Schlumberger | 4.7 | Equipment Failure | Generator Breakdown | RIH (Run In Hole) | Apr-2024 | 4
2024-04-08 | Sagar Bhushan | B-22-HH | ONGC (Own) | 5.7 | Formation/Geological | Formation Damage | Cementing | Apr-2024 | 4
2024-04-08 | Sagar Bhushan | B-15-A | ONGC (Own) | 23.8 | Formation/Geological | H2S Influx | Running BHA | Apr-2024 | 4
2024-04-08 | Sagar Bhushan | B-22-HH | Halliburton | 3.6 | HR/Crew | Crew Shortage | Cementing | Apr-2024 | 4
2024-04-08 | Sagar Prabha | D-11-HH | ONGC (Own) | 6.9 | Equipment Failure | BHA Failure | Running BHA | Apr-2024 | 4
2024-04-08 | Sagar Sampada | E-14-B | ONGC (Own) | 8.7 | Weather/Environment | Heavy Swell (>3m) | Drilling 8.5" | Apr-2024 | 4
2024-04-08 | Sagar Ekta | G-8-HH | ONGC (Own) | 30.8 | Well Control | BOP Test Failure | Testing | Apr-2024 | 4
2024-04-09 | Sagar Prabha | D-7-A | Schlumberger | 3.8 | Equipment Failure | BOP Leak | Drilling 12.25" | Apr-2024 | 4
2024-04-09 | Sagar Kiran | F-6-A | Halliburton | 8.2 | HR/Crew | Competency Issue | Running BHA | Apr-2024 | 4
2024-04-09 | Sagar Ekta | G-8-HH | ONGC (Own) | 11.1 | Weather/Environment | Heavy Swell (>3m) | Testing | Apr-2024 | 4
2024-04-09 | Sagar Ekta | G-13-B | ONGC (Own) | 28.2 | Weather/Environment | Low Visibility/Fog | RIH (Run In Hole) | Apr-2024 | 4
2024-04-10 | Sagar Bhushan | B-22-HH | Schlumberger | 13.2 | Equipment Failure | MWD/LWD Failure | Drilling 12.25" | Apr-2024 | 4
2024-04-10 | Sagar Prabha | D-11-HH | ONGC (Own) | 10.5 | Equipment Failure | Drawworks Issue | Wellbore Survey | Apr-2024 | 4
2024-04-11 | Sagar Bhushan | B-12-HH | ONGC (Own) | 8 | Equipment Failure | MWD/LWD Failure | Running BHA | Apr-2024 | 4
2024-04-11 | Sagar Bhushan | B-15-A | Schlumberger | 10.3 | Equipment Failure | Casing Tong Failure | Completion | Apr-2024 | 4
2024-04-11 | Sagar Ekta | G-1-A | ONGC (Own) | 3.7 | Formation/Geological | Wellbore Instability | POOH (Pull Out of Hole) | Apr-2024 | 4
2024-04-12 | Sagar Bhushan | B-22-HH | Halliburton | 20.7 | Equipment Failure | Casing Tong Failure | Drilling 26" | Apr-2024 | 4
2024-04-12 | Sagar Kiran | F-6-A | ONGC (Own) | 6.1 | HR/Crew | Shift Handover Delay | RIH (Run In Hole) | Apr-2024 | 4
2024-04-12 | Sagar Ekta | G-8-HH | ONGC (Own) | 18.6 | Formation/Geological | Tight Hole | POOH (Pull Out of Hole) | Apr-2024 | 4
2024-04-13 | Sagar Prabha | D-11-HH | Baker Hughes | 4.4 | Equipment Failure | Hook/Block Failure | Completion | Apr-2024 | 4
2024-04-13 | Sagar Prabha | D-11-HH | ONGC (Own) | 9.7 | Third Party/Regulatory | Third Party Certification | RIH (Run In Hole) | Apr-2024 | 4
2024-04-13 | Sagar Sampada | E-5-A | ONGC (Own) | 4.7 | Equipment Failure | Drawworks Issue | Completion | Apr-2024 | 4
2024-04-14 | Sagar Bhushan | B-22-HH | ONGC (Own) | 21.4 | Formation/Geological | Formation Damage | Drilling 8.5" | Apr-2024 | 4
2024-04-14 | Sagar Prabha | D-3-HH | Halliburton | 1.5 | HR/Crew | Crew Sickness | POOH (Pull Out of Hole) | Apr-2024 | 4
2024-04-14 | Sagar Kiran | F-18-HH | ONGC (Own) | 25.7 | Formation/Geological | Wellbore Instability | Testing | Apr-2024 | 4
2024-04-14 | Sagar Kiran | F-18-HH | ONGC (Own) | 28 | Weather/Environment | Cyclone Warning Stand-Down | Running Casing | Apr-2024 | 4
2024-04-15 | Sagar Bhushan | B-22-HH | ONGC (Own) | 7.4 | Equipment Failure | BHA Failure | Drilling 12.25" | Apr-2024 | 4
2024-04-15 | Sagar Bhushan | B-12-HH | Schlumberger | 19.1 | Equipment Failure | Top Drive Malfunction | RIH (Run In Hole) | Apr-2024 | 4
2024-04-15 | Sagar Prabha | D-7-A | ONGC (Own) | 6.7 | Third Party/Regulatory | Third Party Certification | RIH (Run In Hole) | Apr-2024 | 4
2024-04-16 | Sagar Bhushan | B-22-HH | Halliburton | 10.1 | HR/Crew | Shift Handover Delay | Running BHA | Apr-2024 | 4
2024-04-16 | Sagar Prabha | D-3-HH | Baker Hughes | 47.1 | Well Control | Flow Check | Drilling 8.5" | Apr-2024 | 4
2024-04-16 | Sagar Kiran | F-2-HH | Halliburton | 1 | HR/Crew | Shift Handover Delay | Drilling 26" | Apr-2024 | 4
2024-04-17 | Sagar Vijay | C-19-A | ONGC (Own) | 10.7 | Formation/Geological | Wash-Out | Testing | Apr-2024 | 4
2024-04-18 | Sagar Bhushan | B-22-HH | ONGC (Own) | 12 | Equipment Failure | Top Drive Malfunction | RIH (Run In Hole) | Apr-2024 | 4
2024-04-18 | Sagar Bhushan | B-12-HH | ONGC (Own) | 19.1 | Weather/Environment | Cyclone Warning Stand-Down | Wellbore Survey | Apr-2024 | 4
2024-04-18 | Sagar Prabha | D-3-HH | ONGC (Own) | 8.2 | Equipment Failure | Rotary Table Failure | Wellbore Survey | Apr-2024 | 4
2024-04-18 | Sagar Sampada | E-5-A | ONGC (Own) | 32.9 | Weather/Environment | Lightning Stand-Down | RIH (Run In Hole) | Apr-2024 | 4
2024-04-20 | Sagar Bhushan | B-12-HH | Baker Hughes | 17.3 | Equipment Failure | Generator Breakdown | Wellbore Survey | Apr-2024 | 4
2024-04-20 | Sagar Prabha | D-3-HH | ONGC (Own) | 70.4 | Weather/Environment | Low Visibility/Fog | Running BHA | Apr-2024 | 4
2024-04-20 | Sagar Sampada | E-9-HH | ONGC (Own) | 4.4 | Weather/Environment | Heavy Swell (>3m) | Drilling 26" | Apr-2024 | 4
2024-04-20 | Sagar Kiran | F-2-HH | ONGC (Own) | 1.7 | HR/Crew | Crew Shortage | POOH (Pull Out of Hole) | Apr-2024 | 4
2024-04-21 | Sagar Prabha | D-3-HH | ONGC (Own) | 9.3 | Third Party/Regulatory | Environmental Audit | RIH (Run In Hole) | Apr-2024 | 4
2024-04-22 | Sagar Bhushan | B-12-HH | Schlumberger | 15.6 | Equipment Failure | BHA Failure | POOH (Pull Out of Hole) | Apr-2024 | 4
2024-04-22 | Sagar Vijay | C-8-HH | ONGC (Own) | 18 | Formation/Geological | Wellbore Instability | Drilling 12.25" | Apr-2024 | 4
2024-04-22 | Sagar Kiran | F-2-HH | Baker Hughes | 8.8 | Equipment Failure | Pump Breakdown | Wellbore Survey | Apr-2024 | 4
2024-04-23 | Sagar Bhushan | B-12-HH | Schlumberger | 3.8 | Equipment Failure | BOP Leak | Running BHA | Apr-2024 | 4
2024-04-23 | Sagar Bhushan | B-12-HH | Schlumberger | 10.7 | Equipment Failure | Rotary Table Failure | Wellbore Survey | Apr-2024 | 4
2024-04-23 | Sagar Prabha | D-3-HH | ONGC (Own) | 14.5 | Weather/Environment | Lightning Stand-Down | Wellbore Survey | Apr-2024 | 4
2024-04-23 | Sagar Kiran | F-2-HH | Schlumberger | 6.3 | HR/Crew | Competency Issue | Drilling 26" | Apr-2024 | 4
2024-04-24 | Sagar Bhushan | B-15-A | Halliburton | 3.4 | HR/Crew | Crew Sickness | Drilling 26" | Apr-2024 | 4
2024-04-24 | Sagar Sampada | E-9-HH | Baker Hughes | 7 | Equipment Failure | MWD/LWD Failure | POOH (Pull Out of Hole) | Apr-2024 | 4
2024-04-24 | Sagar Sampada | E-5-A | ONGC (Own) | 36.2 | Weather/Environment | Heavy Swell (>3m) | Drilling 8.5" | Apr-2024 | 4
2024-04-24 | Sagar Kiran | F-6-A | ONGC (Own) | 57.2 | Weather/Environment | Cyclone Warning Stand-Down | Running BHA | Apr-2024 | 4
2024-04-24 | Sagar Ekta | G-8-HH | Schlumberger | 25.7 | Logistics/Supply | Drill Bit Delivery Delay | POOH (Pull Out of Hole) | Apr-2024 | 4
2024-04-25 | Sagar Bhushan | B-22-HH | Schlumberger | 7.7 | Equipment Failure | Generator Breakdown | Cementing | Apr-2024 | 4
2024-04-25 | Sagar Bhushan | B-22-HH | ONGC (Own) | 9.5 | Formation/Geological | Formation Damage | Drilling 26" | Apr-2024 | 4
2024-04-25 | Sagar Vijay | C-12-B | ONGC (Own) | 11 | Formation/Geological | Tight Hole | POOH (Pull Out of Hole) | Apr-2024 | 4
2024-04-25 | Sagar Kiran | F-18-HH | Baker Hughes | 6.5 | Equipment Failure | Hook/Block Failure | POOH (Pull Out of Hole) | Apr-2024 | 4
2024-04-25 | Sagar Kiran | F-6-A | Halliburton | 6.2 | HR/Crew | HSE Training Stand-Down | Drilling 26" | Apr-2024 | 4
2024-04-26 | Sagar Bhushan | B-22-HH | ONGC (Own) | 20.7 | Equipment Failure | Rotary Table Failure | RIH (Run In Hole) | Apr-2024 | 4
2024-04-26 | Sagar Vijay | C-8-HH | ONGC (Own) | 6.6 | Weather/Environment | High Wind Speed (>25 knots) | Drilling 8.5" | Apr-2024 | 4
2024-04-26 | Sagar Vijay | C-12-B | ONGC (Own) | 11.9 | Formation/Geological | H2S Influx | Drilling 8.5" | Apr-2024 | 4
2024-04-26 | Sagar Prabha | D-7-A | Baker Hughes | 6.9 | Equipment Failure | BOP Leak | Running Casing | Apr-2024 | 4
2024-04-26 | Sagar Prabha | D-7-A | ONGC (Own) | 2.5 | Third Party/Regulatory | DGMS Inspection | Completion | Apr-2024 | 4
2024-04-26 | Sagar Prabha | D-11-HH | ONGC (Own) | 13.3 | Equipment Failure | Drawworks Issue | Cementing | Apr-2024 | 4
2024-04-26 | Sagar Prabha | D-7-A | Schlumberger | 2.9 | Logistics/Supply | Cement Shortage | Testing | Apr-2024 | 4
2024-04-27 | Sagar Bhushan | B-12-HH | ONGC (Own) | 17.6 | Formation/Geological | Lost Circulation | Running BHA | Apr-2024 | 4
2024-04-27 | Sagar Prabha | D-11-HH | ONGC (Own) | 8.5 | Equipment Failure | Top Drive Malfunction | Cementing | Apr-2024 | 4
2024-04-27 | Sagar Sampada | E-14-B | ONGC (Own) | 47.5 | Weather/Environment | Monsoon Operations Halt | Drilling 26" | Apr-2024 | 4
2024-04-27 | Sagar Sampada | E-9-HH | Halliburton | 3.1 | Logistics/Supply | Cement Shortage | Drilling 8.5" | Apr-2024 | 4
2024-04-27 | Sagar Sampada | E-5-A | ONGC (Own) | 16.1 | Weather/Environment | Cyclone Warning Stand-Down | RIH (Run In Hole) | Apr-2024 | 4
2024-04-28 | Sagar Ekta | G-1-A | ONGC (Own) | 11.1 | Formation/Geological | Kick/Well Control Event | Drilling 26" | Apr-2024 | 4
2024-04-29 | Sagar Bhushan | B-22-HH | ONGC (Own) | 60.2 | Weather/Environment | Lightning Stand-Down | POOH (Pull Out of Hole) | Apr-2024 | 4
2024-04-29 | Sagar Prabha | D-7-A | Baker Hughes | 2.8 | Equipment Failure | Drawworks Issue | Wellbore Survey | Apr-2024 | 4
2024-04-29 | Sagar Prabha | D-7-A | Halliburton | 21.1 | Logistics/Supply | Chemical Supply Delay | Drilling 8.5" | Apr-2024 | 4
2024-04-29 | Sagar Kiran | F-6-A | ONGC (Own) | 8.4 | Formation/Geological | Wellbore Instability | Drilling 12.25" | Apr-2024 | 4
2024-04-29 | Sagar Kiran | F-2-HH | Halliburton | 6.8 | HR/Crew | Crew Shortage | Running Casing | Apr-2024 | 4
2024-04-30 | Sagar Bhushan | B-22-HH | ONGC (Own) | 61.7 | Well Control | Kick Observation & Shut-In | Drilling 26" | Apr-2024 | 4
2024-04-30 | Sagar Kiran | F-2-HH | Schlumberger | 7.2 | HR/Crew | Shift Handover Delay | Drilling 26" | Apr-2024 | 4
2024-05-01 | Sagar Sampada | E-5-A | Halliburton | 8.3 | Equipment Failure | BOP Leak | Completion | May-2024 | 5
2024-05-02 | Sagar Prabha | D-11-HH | Schlumberger | 6.6 | Equipment Failure | MWD/LWD Failure | Running Casing | May-2024 | 5
2024-05-02 | Sagar Kiran | F-18-HH | Baker Hughes | 8.3 | HR/Crew | Crew Shortage | Wellbore Survey | May-2024 | 5
2024-05-02 | Sagar Kiran | F-2-HH | Schlumberger | 8.3 | HR/Crew | Crew Change Delay | Drilling 26" | May-2024 | 5
2024-05-03 | Sagar Vijay | C-19-A | ONGC (Own) | 18.4 | Formation/Geological | Lost Circulation | Drilling 8.5" | May-2024 | 5
2024-05-03 | Sagar Ekta | G-8-HH | ONGC (Own) | 9.6 | Equipment Failure | BHA Failure | Running Casing | May-2024 | 5
2024-05-04 | Sagar Bhushan | B-12-HH | ONGC (Own) | 7.9 | Formation/Geological | Stuck Pipe | Running Casing | May-2024 | 5
2024-05-04 | Sagar Vijay | C-12-B | ONGC (Own) | 20.1 | Formation/Geological | Stuck Pipe | Testing | May-2024 | 5
2024-05-04 | Sagar Vijay | C-8-HH | ONGC (Own) | 6.4 | Well Control | Well Kill Operation | Running BHA | May-2024 | 5
2024-05-04 | Sagar Ekta | G-8-HH | Schlumberger | 11.2 | Equipment Failure | Drawworks Issue | POOH (Pull Out of Hole) | May-2024 | 5
2024-05-04 | Sagar Ekta | G-8-HH | ONGC (Own) | 4.7 | Formation/Geological | Wash-Out | Completion | May-2024 | 5
2024-05-05 | Sagar Prabha | D-11-HH | Baker Hughes | 17.6 | Equipment Failure | MWD/LWD Failure | Cementing | May-2024 | 5
2024-05-05 | Sagar Sampada | E-14-B | ONGC (Own) | 2.3 | HR/Crew | Crew Change Delay | Testing | May-2024 | 5
2024-05-06 | Sagar Bhushan | B-15-A | Halliburton | 5.1 | HR/Crew | Competency Issue | Completion | May-2024 | 5
2024-05-06 | Sagar Bhushan | B-12-HH | Baker Hughes | 22.4 | Equipment Failure | Top Drive Malfunction | Completion | May-2024 | 5
2024-05-06 | Sagar Kiran | F-2-HH | Halliburton | 2.2 | HR/Crew | Crew Shortage | Drilling 12.25" | May-2024 | 5
2024-05-06 | Sagar Kiran | F-6-A | ONGC (Own) | 6.2 | HR/Crew | Crew Shortage | Drilling 8.5" | May-2024 | 5
2024-05-06 | Sagar Kiran | F-18-HH | ONGC (Own) | 8.6 | HR/Crew | Crew Shortage | Cementing | May-2024 | 5
2024-05-07 | Sagar Kiran | F-2-HH | Halliburton | 3.4 | HR/Crew | Shift Handover Delay | Drilling 12.25" | May-2024 | 5
2024-05-08 | Sagar Bhushan | B-15-A | Halliburton | 22.3 | Equipment Failure | MWD/LWD Failure | POOH (Pull Out of Hole) | May-2024 | 5
2024-05-08 | Sagar Sampada | E-5-A | Baker Hughes | 33.1 | Well Control | Well Kill Operation | Wellbore Survey | May-2024 | 5
2024-05-08 | Sagar Sampada | E-9-HH | ONGC (Own) | 5.4 | Weather/Environment | Low Visibility/Fog | POOH (Pull Out of Hole) | May-2024 | 5
2024-05-09 | Sagar Ekta | G-8-HH | ONGC (Own) | 15.7 | Weather/Environment | Low Visibility/Fog | POOH (Pull Out of Hole) | May-2024 | 5
2024-05-10 | Sagar Bhushan | B-15-A | ONGC (Own) | 13.5 | Weather/Environment | High Wind Speed (>25 knots) | Running Casing | May-2024 | 5
2024-05-10 | Sagar Bhushan | B-15-A | ONGC (Own) | 28 | Formation/Geological | H2S Influx | POOH (Pull Out of Hole) | May-2024 | 5
2024-05-10 | Sagar Vijay | C-12-B | ONGC (Own) | 17.9 | Formation/Geological | Tight Hole | Wellbore Survey | May-2024 | 5
2024-05-10 | Sagar Prabha | D-7-A | Schlumberger | 11 | Equipment Failure | Generator Breakdown | Completion | May-2024 | 5
2024-05-10 | Sagar Sampada | E-5-A | ONGC (Own) | 5.7 | Formation/Geological | Tight Hole | Wellbore Survey | May-2024 | 5
2024-05-11 | Sagar Bhushan | B-22-HH | ONGC (Own) | 58.1 | Weather/Environment | Monsoon Operations Halt | RIH (Run In Hole) | May-2024 | 5
2024-05-11 | Sagar Bhushan | B-22-HH | ONGC (Own) | 11.1 | Formation/Geological | Kick/Well Control Event | Running Casing | May-2024 | 5
2024-05-11 | Sagar Prabha | D-7-A | Schlumberger | 9.1 | Equipment Failure | BOP Leak | RIH (Run In Hole) | May-2024 | 5
2024-05-11 | Sagar Prabha | D-11-HH | Schlumberger | 16.5 | Equipment Failure | Casing Tong Failure | POOH (Pull Out of Hole) | May-2024 | 5
2024-05-11 | Sagar Kiran | F-18-HH | ONGC (Own) | 9.4 | HR/Crew | HSE Training Stand-Down | Completion | May-2024 | 5
2024-05-11 | Sagar Ekta | G-1-A | ONGC (Own) | 39.2 | Well Control | Well Kill Operation | POOH (Pull Out of Hole) | May-2024 | 5
2024-05-12 | Sagar Vijay | C-19-A | ONGC (Own) | 8.4 | Formation/Geological | Lost Circulation | Cementing | May-2024 | 5
2024-05-12 | Sagar Vijay | C-8-HH | ONGC (Own) | 5.7 | Formation/Geological | H2S Influx | Drilling 12.25" | May-2024 | 5
2024-05-13 | Sagar Bhushan | B-12-HH | ONGC (Own) | 8.2 | Equipment Failure | BHA Failure | Drilling 12.25" | May-2024 | 5
2024-05-13 | Sagar Kiran | F-6-A | ONGC (Own) | 4.9 | HR/Crew | Shift Handover Delay | Drilling 26" | May-2024 | 5
2024-05-14 | Sagar Vijay | C-19-A | Baker Hughes | 4.2 | HR/Crew | Crew Shortage | Drilling 12.25" | May-2024 | 5
2024-05-15 | Sagar Kiran | F-6-A | Schlumberger | 5.9 | HR/Crew | Crew Change Delay | Cementing | May-2024 | 5
2024-05-15 | Sagar Ekta | G-13-B | ONGC (Own) | 10.6 | Weather/Environment | Heavy Swell (>3m) | Testing | May-2024 | 5
2024-05-16 | Sagar Bhushan | B-22-HH | ONGC (Own) | 10.8 | Well Control | Well Kill Operation | Cementing | May-2024 | 5
2024-05-16 | Sagar Kiran | F-18-HH | ONGC (Own) | 8.2 | HR/Crew | Shift Handover Delay | Completion | May-2024 | 5
2024-05-17 | Sagar Bhushan | B-22-HH | ONGC (Own) | 14 | Formation/Geological | Kick/Well Control Event | Drilling 26" | May-2024 | 5
2024-05-17 | Sagar Vijay | C-12-B | Baker Hughes | 9.2 | Equipment Failure | Hook/Block Failure | Wellbore Survey | May-2024 | 5
2024-05-17 | Sagar Sampada | E-14-B | ONGC (Own) | 8.6 | Formation/Geological | Formation Damage | Drilling 12.25" | May-2024 | 5
2024-05-17 | Sagar Kiran | F-6-A | Schlumberger | 3.9 | Equipment Failure | Pump Breakdown | Running BHA | May-2024 | 5
2024-05-17 | Sagar Ekta | G-1-A | Schlumberger | 10.4 | Logistics/Supply | Drill Bit Delivery Delay | Testing | May-2024 | 5
2024-05-18 | Sagar Bhushan | B-12-HH | Schlumberger | 8.1 | HR/Crew | HSE Training Stand-Down | Drilling 8.5" | May-2024 | 5
2024-05-18 | Sagar Prabha | D-11-HH | ONGC (Own) | 61.6 | Weather/Environment | Cyclone Warning Stand-Down | Running Casing | May-2024 | 5
2024-05-18 | Sagar Prabha | D-3-HH | ONGC (Own) | 18.1 | Formation/Geological | Kick/Well Control Event | Cementing | May-2024 | 5
2024-05-20 | Sagar Vijay | C-19-A | Schlumberger | 18.2 | Logistics/Supply | Chemical Supply Delay | Wellbore Survey | May-2024 | 5
2024-05-20 | Sagar Kiran | F-2-HH | ONGC (Own) | 13.6 | Formation/Geological | Formation Damage | Completion | May-2024 | 5
2024-05-21 | Sagar Bhushan | B-22-HH | Schlumberger | 14 | Equipment Failure | Rotary Table Failure | POOH (Pull Out of Hole) | May-2024 | 5
2024-05-21 | Sagar Prabha | D-7-A | Halliburton | 7.4 | Equipment Failure | BHA Failure | POOH (Pull Out of Hole) | May-2024 | 5
2024-05-21 | Sagar Kiran | F-6-A | ONGC (Own) | 2.8 | HR/Crew | Crew Shortage | Testing | May-2024 | 5
2024-05-21 | Sagar Ekta | G-1-A | ONGC (Own) | 30.6 | Logistics/Supply | Vessel Non-Availability | Drilling 26" | May-2024 | 5
2024-05-22 | Sagar Ekta | G-8-HH | Schlumberger | 25.3 | Logistics/Supply | Cement Shortage | Testing | May-2024 | 5
2024-05-23 | Sagar Bhushan | B-22-HH | Halliburton | 8.7 | Equipment Failure | Pump Breakdown | Cementing | May-2024 | 5
2024-05-23 | Sagar Sampada | E-14-B | Halliburton | 8.2 | Equipment Failure | Rotary Table Failure | Drilling 26" | May-2024 | 5
2024-05-23 | Sagar Ekta | G-1-A | Schlumberger | 6.2 | HR/Crew | Crew Sickness | Drilling 8.5" | May-2024 | 5
2024-05-23 | Sagar Ekta | G-13-B | Baker Hughes | 2.5 | HR/Crew | Shift Handover Delay | RIH (Run In Hole) | May-2024 | 5
2024-05-24 | Sagar Kiran | F-6-A | ONGC (Own) | 1.3 | HR/Crew | Crew Shortage | RIH (Run In Hole) | May-2024 | 5
2024-05-25 | Sagar Bhushan | B-15-A | ONGC (Own) | 6.7 | Equipment Failure | Pump Breakdown | Wellbore Survey | May-2024 | 5
2024-05-25 | Sagar Prabha | D-7-A | Schlumberger | 4.8 | Equipment Failure | Rotary Table Failure | RIH (Run In Hole) | May-2024 | 5
2024-05-25 | Sagar Sampada | E-14-B | ONGC (Own) | 7.4 | Formation/Geological | H2S Influx | Testing | May-2024 | 5
2024-05-25 | Sagar Sampada | E-9-HH | ONGC (Own) | 25.4 | Weather/Environment | High Wind Speed (>25 knots) | Wellbore Survey | May-2024 | 5
2024-05-25 | Sagar Sampada | E-9-HH | ONGC (Own) | 8.5 | Weather/Environment | High Wind Speed (>25 knots) | Completion | May-2024 | 5
2024-05-25 | Sagar Kiran | F-18-HH | ONGC (Own) | 3.2 | Equipment Failure | Casing Tong Failure | Completion | May-2024 | 5
2024-05-27 | Sagar Bhushan | B-15-A | ONGC (Own) | 66.7 | Weather/Environment | Low Visibility/Fog | Running BHA | May-2024 | 5
2024-05-27 | Sagar Vijay | C-12-B | Schlumberger | 3.5 | HR/Crew | Crew Shortage | Completion | May-2024 | 5
2024-05-27 | Sagar Kiran | F-6-A | Schlumberger | 1.9 | HR/Crew | Crew Shortage | RIH (Run In Hole) | May-2024 | 5
2024-05-28 | Sagar Ekta | G-1-A | ONGC (Own) | 17.5 | Formation/Geological | Tight Hole | Drilling 26" | May-2024 | 5
2024-05-29 | Sagar Vijay | C-19-A | Halliburton | 3.3 | Equipment Failure | Rotary Table Failure | Testing | May-2024 | 5
2024-05-29 | Sagar Sampada | E-14-B | Baker Hughes | 9.2 | Equipment Failure | Rotary Table Failure | Drilling 12.25" | May-2024 | 5
2024-05-29 | Sagar Kiran | F-6-A | Baker Hughes | 9.2 | HR/Crew | Crew Shortage | POOH (Pull Out of Hole) | May-2024 | 5
2024-05-29 | Sagar Kiran | F-6-A | Baker Hughes | 7.1 | Equipment Failure | Hook/Block Failure | Running BHA | May-2024 | 5
2024-05-29 | Sagar Kiran | F-2-HH | ONGC (Own) | 4.5 | HR/Crew | HSE Training Stand-Down | Testing | May-2024 | 5
2024-05-29 | Sagar Ekta | G-13-B | ONGC (Own) | 7.4 | Equipment Failure | Drawworks Issue | Cementing | May-2024 | 5
2024-05-30 | Sagar Prabha | D-3-HH | Schlumberger | 3.9 | Equipment Failure | Generator Breakdown | RIH (Run In Hole) | May-2024 | 5
2024-05-30 | Sagar Prabha | D-11-HH | ONGC (Own) | 55.6 | Weather/Environment | High Wind Speed (>25 knots) | Drilling 26" | May-2024 | 5
2024-05-30 | Sagar Sampada | E-9-HH | ONGC (Own) | 48.1 | Weather/Environment | Heavy Swell (>3m) | Drilling 26" | May-2024 | 5
2024-05-31 | Sagar Bhushan | B-22-HH | Halliburton | 31 | Logistics/Supply | Chemical Supply Delay | Drilling 12.25" | May-2024 | 5
2024-05-31 | Sagar Prabha | D-7-A | ONGC (Own) | 10.1 | Formation/Geological | Kick/Well Control Event | Completion | May-2024 | 5
2024-05-31 | Sagar Kiran | F-6-A | Halliburton | 14.2 | Equipment Failure | Top Drive Malfunction | Testing | May-2024 | 5
2024-05-31 | Sagar Kiran | F-2-HH | Schlumberger | 6 | Logistics/Supply | Casing Delivery Delay | Drilling 26" | May-2024 | 5
2024-05-31 | Sagar Kiran | F-18-HH | Halliburton | 7.3 | HR/Crew | Competency Issue | Completion | May-2024 | 5
2024-06-01 | Sagar Bhushan | B-15-A | Schlumberger | 27.6 | Equipment Failure | Hook/Block Failure | RIH (Run In Hole) | Jun-2024 | 6
2024-06-01 | Sagar Sampada | E-14-B | Schlumberger | 2.3 | HR/Crew | Shift Handover Delay | RIH (Run In Hole) | Jun-2024 | 6
2024-06-02 | Sagar Vijay | C-8-HH | ONGC (Own) | 23.2 | Formation/Geological | Lost Circulation | Wellbore Survey | Jun-2024 | 6
2024-06-02 | Sagar Prabha | D-7-A | ONGC (Own) | 13.2 | Equipment Failure | BHA Failure | Wellbore Survey | Jun-2024 | 6
2024-06-02 | Sagar Kiran | F-2-HH | ONGC (Own) | 26.7 | Formation/Geological | Kick/Well Control Event | Drilling 12.25" | Jun-2024 | 6
2024-06-02 | Sagar Kiran | F-6-A | Schlumberger | 6.6 | HR/Crew | Crew Sickness | Wellbore Survey | Jun-2024 | 6
2024-06-02 | Sagar Ekta | G-1-A | Schlumberger | 30.8 | Logistics/Supply | Drill Bit Delivery Delay | RIH (Run In Hole) | Jun-2024 | 6
2024-06-03 | Sagar Bhushan | B-15-A | Schlumberger | 19.4 | Equipment Failure | Top Drive Malfunction | Drilling 8.5" | Jun-2024 | 6
2024-06-03 | Sagar Vijay | C-12-B | ONGC (Own) | 20.1 | Formation/Geological | Kick/Well Control Event | Drilling 8.5" | Jun-2024 | 6
2024-06-03 | Sagar Sampada | E-5-A | ONGC (Own) | 32.7 | Weather/Environment | Lightning Stand-Down | Drilling 26" | Jun-2024 | 6
2024-06-03 | Sagar Kiran | F-2-HH | ONGC (Own) | 8.5 | Formation/Geological | Wash-Out | Running BHA | Jun-2024 | 6
2024-06-04 | Sagar Prabha | D-7-A | ONGC (Own) | 57 | Weather/Environment | Lightning Stand-Down | Testing | Jun-2024 | 6
2024-06-04 | Sagar Ekta | G-13-B | ONGC (Own) | 22.6 | Logistics/Supply | Casing Delivery Delay | Running BHA | Jun-2024 | 6
2024-06-05 | Sagar Prabha | D-11-HH | Schlumberger | 4.8 | Equipment Failure | Hook/Block Failure | RIH (Run In Hole) | Jun-2024 | 6
2024-06-05 | Sagar Sampada | E-14-B | ONGC (Own) | 8.6 | Equipment Failure | Drawworks Issue | Wellbore Survey | Jun-2024 | 6
2024-06-05 | Sagar Kiran | F-2-HH | ONGC (Own) | 84.8 | Weather/Environment | Low Visibility/Fog | Drilling 26" | Jun-2024 | 6
2024-06-05 | Sagar Kiran | F-2-HH | ONGC (Own) | 1.9 | HR/Crew | Crew Sickness | Testing | Jun-2024 | 6
2024-06-06 | Sagar Vijay | C-19-A | ONGC (Own) | 5.8 | Formation/Geological | Formation Damage | Running BHA | Jun-2024 | 6
2024-06-06 | Sagar Vijay | C-19-A | ONGC (Own) | 7.5 | Formation/Geological | Kick/Well Control Event | Drilling 12.25" | Jun-2024 | 6
2024-06-06 | Sagar Sampada | E-14-B | ONGC (Own) | 62 | Weather/Environment | Monsoon Operations Halt | RIH (Run In Hole) | Jun-2024 | 6
2024-06-06 | Sagar Sampada | E-5-A | ONGC (Own) | 23.3 | Weather/Environment | Low Visibility/Fog | Drilling 12.25" | Jun-2024 | 6
2024-06-06 | Sagar Kiran | F-18-HH | ONGC (Own) | 9.7 | HR/Crew | Crew Shortage | Drilling 26" | Jun-2024 | 6
2024-06-06 | Sagar Kiran | F-18-HH | ONGC (Own) | 1.6 | HR/Crew | Crew Change Delay | Running BHA | Jun-2024 | 6
2024-06-06 | Sagar Kiran | F-2-HH | Halliburton | 15 | Equipment Failure | Hook/Block Failure | Running Casing | Jun-2024 | 6
2024-06-07 | Sagar Vijay | C-12-B | ONGC (Own) | 14.1 | Formation/Geological | Tight Hole | Cementing | Jun-2024 | 6
2024-06-07 | Sagar Kiran | F-6-A | Halliburton | 2.9 | HR/Crew | Crew Sickness | Running Casing | Jun-2024 | 6
2024-06-07 | Sagar Kiran | F-2-HH | ONGC (Own) | 7.3 | Formation/Geological | Wellbore Instability | Drilling 8.5" | Jun-2024 | 6
2024-06-08 | Sagar Bhushan | B-22-HH | Schlumberger | 33.4 | Equipment Failure | MWD/LWD Failure | Running BHA | Jun-2024 | 6
2024-06-08 | Sagar Prabha | D-7-A | Halliburton | 25.1 | Equipment Failure | Drawworks Issue | Running BHA | Jun-2024 | 6
2024-06-08 | Sagar Prabha | D-7-A | Baker Hughes | 50.4 | Well Control | Flow Check | Wellbore Survey | Jun-2024 | 6
2024-06-09 | Sagar Sampada | E-9-HH | ONGC (Own) | 18 | Logistics/Supply | Cement Shortage | Running Casing | Jun-2024 | 6
2024-06-10 | Sagar Vijay | C-19-A | ONGC (Own) | 5.5 | Formation/Geological | Tight Hole | Testing | Jun-2024 | 6
2024-06-10 | Sagar Sampada | E-9-HH | Schlumberger | 9.2 | Equipment Failure | MWD/LWD Failure | Completion | Jun-2024 | 6
2024-06-10 | Sagar Kiran | F-2-HH | ONGC (Own) | 14.6 | Logistics/Supply | Chemical Supply Delay | Running BHA | Jun-2024 | 6
2024-06-10 | Sagar Kiran | F-2-HH | Schlumberger | 14.7 | Logistics/Supply | Cement Shortage | Drilling 26" | Jun-2024 | 6
2024-06-10 | Sagar Ekta | G-8-HH | Schlumberger | 15.3 | Equipment Failure | BHA Failure | Drilling 8.5" | Jun-2024 | 6
2024-06-11 | Sagar Kiran | F-6-A | ONGC (Own) | 28.9 | Weather/Environment | Monsoon Operations Halt | Drilling 8.5" | Jun-2024 | 6
2024-06-12 | Sagar Vijay | C-12-B | ONGC (Own) | 11.6 | Formation/Geological | H2S Influx | Drilling 8.5" | Jun-2024 | 6
2024-06-12 | Sagar Prabha | D-7-A | Halliburton | 9.5 | Equipment Failure | Drawworks Issue | Testing | Jun-2024 | 6
2024-06-12 | Sagar Kiran | F-18-HH | Schlumberger | 4.2 | HR/Crew | Crew Change Delay | Drilling 12.25" | Jun-2024 | 6
2024-06-12 | Sagar Kiran | F-6-A | Schlumberger | 7.5 | HR/Crew | Competency Issue | Running BHA | Jun-2024 | 6
2024-06-12 | Sagar Ekta | G-13-B | Schlumberger | 36.6 | Logistics/Supply | Chemical Supply Delay | RIH (Run In Hole) | Jun-2024 | 6
2024-06-13 | Sagar Bhushan | B-22-HH | Baker Hughes | 17.5 | Equipment Failure | BOP Leak | RIH (Run In Hole) | Jun-2024 | 6
2024-06-13 | Sagar Sampada | E-9-HH | ONGC (Own) | 33.3 | Weather/Environment | Heavy Swell (>3m) | Drilling 26" | Jun-2024 | 6
2024-06-14 | Sagar Bhushan | B-12-HH | Baker Hughes | 7.2 | HR/Crew | Competency Issue | Wellbore Survey | Jun-2024 | 6
2024-06-14 | Sagar Sampada | E-5-A | ONGC (Own) | 54.2 | Weather/Environment | Monsoon Operations Halt | Cementing | Jun-2024 | 6
2024-06-14 | Sagar Kiran | F-18-HH | ONGC (Own) | 11.2 | Equipment Failure | Top Drive Malfunction | Drilling 26" | Jun-2024 | 6
2024-06-14 | Sagar Ekta | G-13-B | ONGC (Own) | 5.7 | Formation/Geological | Wellbore Instability | Running BHA | Jun-2024 | 6
2024-06-15 | Sagar Bhushan | B-15-A | Baker Hughes | 26 | Equipment Failure | Hook/Block Failure | Drilling 12.25" | Jun-2024 | 6
2024-06-15 | Sagar Bhushan | B-15-A | ONGC (Own) | 15.3 | Equipment Failure | Casing Tong Failure | Running Casing | Jun-2024 | 6
2024-06-15 | Sagar Vijay | C-8-HH | ONGC (Own) | 27.3 | Weather/Environment | Cyclone Warning Stand-Down | POOH (Pull Out of Hole) | Jun-2024 | 6
2024-06-15 | Sagar Vijay | C-12-B | ONGC (Own) | 8.1 | Weather/Environment | Monsoon Operations Halt | POOH (Pull Out of Hole) | Jun-2024 | 6
2024-06-15 | Sagar Prabha | D-3-HH | ONGC (Own) | 13.2 | Equipment Failure | Casing Tong Failure | RIH (Run In Hole) | Jun-2024 | 6
2024-06-15 | Sagar Ekta | G-13-B | Schlumberger | 14.7 | Equipment Failure | Hook/Block Failure | Testing | Jun-2024 | 6
2024-06-16 | Sagar Bhushan | B-22-HH | Halliburton | 16.8 | Equipment Failure | Top Drive Malfunction | Drilling 8.5" | Jun-2024 | 6
2024-06-16 | Sagar Vijay | C-12-B | ONGC (Own) | 13.3 | Formation/Geological | Stuck Pipe | Wellbore Survey | Jun-2024 | 6
2024-06-16 | Sagar Prabha | D-11-HH | Schlumberger | 4.9 | Equipment Failure | Generator Breakdown | Wellbore Survey | Jun-2024 | 6
2024-06-16 | Sagar Kiran | F-6-A | ONGC (Own) | 96 | Weather/Environment | Lightning Stand-Down | POOH (Pull Out of Hole) | Jun-2024 | 6
2024-06-17 | Sagar Vijay | C-19-A | Halliburton | 3.3 | Equipment Failure | Casing Tong Failure | Wellbore Survey | Jun-2024 | 6
2024-06-17 | Sagar Vijay | C-19-A | ONGC (Own) | 5.4 | Formation/Geological | Wash-Out | Drilling 12.25" | Jun-2024 | 6
2024-06-17 | Sagar Prabha | D-7-A | Schlumberger | 13.5 | Equipment Failure | Top Drive Malfunction | Testing | Jun-2024 | 6
2024-06-17 | Sagar Prabha | D-11-HH | ONGC (Own) | 27.9 | Formation/Geological | H2S Influx | POOH (Pull Out of Hole) | Jun-2024 | 6
2024-06-17 | Sagar Kiran | F-6-A | ONGC (Own) | 39.1 | Well Control | Kick Observation & Shut-In | Drilling 26" | Jun-2024 | 6
2024-06-17 | Sagar Ekta | G-8-HH | Schlumberger | 15.1 | Equipment Failure | Generator Breakdown | Drilling 26" | Jun-2024 | 6
2024-06-17 | Sagar Ekta | G-8-HH | ONGC (Own) | 20.6 | Formation/Geological | Tight Hole | Drilling 26" | Jun-2024 | 6
2024-06-18 | Sagar Sampada | E-14-B | ONGC (Own) | 8.7 | Weather/Environment | Lightning Stand-Down | Running BHA | Jun-2024 | 6
2024-06-19 | Sagar Vijay | C-19-A | Baker Hughes | 8 | HR/Crew | Crew Sickness | Running BHA | Jun-2024 | 6
2024-06-19 | Sagar Vijay | C-8-HH | ONGC (Own) | 8.2 | Well Control | Flow Check | Running BHA | Jun-2024 | 6
2024-06-19 | Sagar Ekta | G-13-B | Halliburton | 7.6 | HR/Crew | Crew Change Delay | Testing | Jun-2024 | 6
2024-06-20 | Sagar Bhushan | B-15-A | ONGC (Own) | 70.1 | Weather/Environment | Low Visibility/Fog | Drilling 12.25" | Jun-2024 | 6
2024-06-20 | Sagar Bhushan | B-22-HH | ONGC (Own) | 20.5 | Formation/Geological | Wash-Out | Completion | Jun-2024 | 6
2024-06-20 | Sagar Prabha | D-7-A | Halliburton | 10.5 | HR/Crew | HSE Training Stand-Down | Wellbore Survey | Jun-2024 | 6
2024-06-21 | Sagar Vijay | C-19-A | Baker Hughes | 40.1 | Well Control | Well Kill Operation | Wellbore Survey | Jun-2024 | 6
2024-06-21 | Sagar Kiran | F-18-HH | Halliburton | 3 | HR/Crew | HSE Training Stand-Down | Testing | Jun-2024 | 6
2024-06-21 | Sagar Ekta | G-13-B | Baker Hughes | 7.9 | Equipment Failure | BOP Leak | RIH (Run In Hole) | Jun-2024 | 6
2024-06-22 | Sagar Bhushan | B-22-HH | Baker Hughes | 24 | Equipment Failure | Top Drive Malfunction | Wellbore Survey | Jun-2024 | 6
2024-06-22 | Sagar Bhushan | B-12-HH | Halliburton | 21.3 | Equipment Failure | Drawworks Issue | Running Casing | Jun-2024 | 6
2024-06-22 | Sagar Bhushan | B-15-A | ONGC (Own) | 66.1 | Weather/Environment | High Wind Speed (>25 knots) | Completion | Jun-2024 | 6
2024-06-22 | Sagar Bhushan | B-22-HH | Baker Hughes | 11.1 | Equipment Failure | BHA Failure | Wellbore Survey | Jun-2024 | 6
2024-06-23 | Sagar Bhushan | B-12-HH | Halliburton | 17 | Equipment Failure | Hook/Block Failure | Cementing | Jun-2024 | 6
2024-06-23 | Sagar Prabha | D-11-HH | ONGC (Own) | 6 | Equipment Failure | Drawworks Issue | Cementing | Jun-2024 | 6
2024-06-23 | Sagar Kiran | F-2-HH | ONGC (Own) | 96 | Weather/Environment | High Wind Speed (>25 knots) | Completion | Jun-2024 | 6
2024-06-23 | Sagar Kiran | F-18-HH | ONGC (Own) | 51.9 | Well Control | Well Kill Operation | RIH (Run In Hole) | Jun-2024 | 6
2024-06-23 | Sagar Ekta | G-13-B | ONGC (Own) | 74 | Weather/Environment | Lightning Stand-Down | Drilling 8.5" | Jun-2024 | 6
2024-06-23 | Sagar Ekta | G-13-B | Schlumberger | 14.1 | Logistics/Supply | Cement Shortage | Drilling 8.5" | Jun-2024 | 6
2024-06-24 | Sagar Vijay | C-8-HH | ONGC (Own) | 16 | Formation/Geological | Wellbore Instability | Drilling 8.5" | Jun-2024 | 6
2024-06-24 | Sagar Prabha | D-7-A | ONGC (Own) | 26.6 | Formation/Geological | Kick/Well Control Event | Drilling 26" | Jun-2024 | 6
2024-06-24 | Sagar Sampada | E-9-HH | ONGC (Own) | 18.4 | Formation/Geological | Wash-Out | Running Casing | Jun-2024 | 6
2024-06-24 | Sagar Kiran | F-2-HH | Baker Hughes | 28.8 | Well Control | BOP Test Failure | Drilling 8.5" | Jun-2024 | 6
2024-06-24 | Sagar Kiran | F-6-A | Schlumberger | 1.9 | HR/Crew | Crew Change Delay | Drilling 8.5" | Jun-2024 | 6
2024-06-25 | Sagar Bhushan | B-22-HH | Baker Hughes | 15.1 | HR/Crew | Crew Change Delay | Drilling 26" | Jun-2024 | 6
2024-06-25 | Sagar Vijay | C-12-B | Schlumberger | 3 | Equipment Failure | Hook/Block Failure | Running Casing | Jun-2024 | 6
2024-06-25 | Sagar Kiran | F-18-HH | Baker Hughes | 4.3 | Equipment Failure | Top Drive Malfunction | Running BHA | Jun-2024 | 6
2024-06-25 | Sagar Ekta | G-8-HH | Baker Hughes | 48.4 | Well Control | BOP Test Failure | RIH (Run In Hole) | Jun-2024 | 6
2024-06-25 | Sagar Ekta | G-1-A | ONGC (Own) | 34.3 | Weather/Environment | Cyclone Warning Stand-Down | Drilling 12.25" | Jun-2024 | 6
2024-06-25 | Sagar Ekta | G-13-B | ONGC (Own) | 49.3 | Weather/Environment | Monsoon Operations Halt | Drilling 12.25" | Jun-2024 | 6
2024-06-26 | Sagar Vijay | C-12-B | ONGC (Own) | 5.6 | Formation/Geological | Kick/Well Control Event | Drilling 8.5" | Jun-2024 | 6
2024-06-26 | Sagar Kiran | F-2-HH | Schlumberger | 21.8 | Logistics/Supply | Completion Equipment Delay | POOH (Pull Out of Hole) | Jun-2024 | 6
2024-06-26 | Sagar Ekta | G-8-HH | ONGC (Own) | 4.7 | Third Party/Regulatory | Environmental Audit | POOH (Pull Out of Hole) | Jun-2024 | 6
2024-06-26 | Sagar Ekta | G-1-A | ONGC (Own) | 22.4 | Formation/Geological | H2S Influx | RIH (Run In Hole) | Jun-2024 | 6
2024-06-26 | Sagar Ekta | G-8-HH | ONGC (Own) | 6.8 | HR/Crew | Competency Issue | Running BHA | Jun-2024 | 6
2024-06-27 | Sagar Bhushan | B-22-HH | Baker Hughes | 24.2 | Equipment Failure | Rotary Table Failure | Running BHA | Jun-2024 | 6
2024-06-27 | Sagar Vijay | C-12-B | ONGC (Own) | 23.8 | Formation/Geological | H2S Influx | Testing | Jun-2024 | 6
2024-06-27 | Sagar Sampada | E-9-HH | ONGC (Own) | 54.1 | Weather/Environment | Monsoon Operations Halt | Cementing | Jun-2024 | 6
2024-06-27 | Sagar Sampada | E-14-B | Baker Hughes | 22.1 | Well Control | Kick Observation & Shut-In | Drilling 12.25" | Jun-2024 | 6
2024-06-27 | Sagar Ekta | G-13-B | ONGC (Own) | 19.2 | Logistics/Supply | Completion Equipment Delay | Drilling 26" | Jun-2024 | 6
2024-06-27 | Sagar Ekta | G-1-A | Schlumberger | 40.8 | Logistics/Supply | Drill Bit Delivery Delay | POOH (Pull Out of Hole) | Jun-2024 | 6
2024-06-28 | Sagar Bhushan | B-12-HH | Baker Hughes | 12.1 | Equipment Failure | Top Drive Malfunction | Running BHA | Jun-2024 | 6
2024-06-28 | Sagar Vijay | C-8-HH | Baker Hughes | 10.7 | Equipment Failure | MWD/LWD Failure | Running BHA | Jun-2024 | 6
2024-06-28 | Sagar Prabha | D-3-HH | Schlumberger | 16 | Equipment Failure | Casing Tong Failure | Wellbore Survey | Jun-2024 | 6
2024-06-28 | Sagar Kiran | F-18-HH | ONGC (Own) | 96 | Weather/Environment | Lightning Stand-Down | Testing | Jun-2024 | 6
2024-06-29 | Sagar Bhushan | B-15-A | Schlumberger | 3.9 | HR/Crew | Crew Change Delay | POOH (Pull Out of Hole) | Jun-2024 | 6
2024-06-30 | Sagar Bhushan | B-15-A | ONGC (Own) | 39.6 | Formation/Geological | Wellbore Instability | Completion | Jun-2024 | 6
2024-06-30 | Sagar Vijay | C-19-A | ONGC (Own) | 3.7 | Formation/Geological | Kick/Well Control Event | Cementing | Jun-2024 | 6
2024-06-30 | Sagar Prabha | D-7-A | ONGC (Own) | 35.5 | Formation/Geological | Stuck Pipe | Drilling 8.5" | Jun-2024 | 6
2024-06-30 | Sagar Prabha | D-7-A | Baker Hughes | 13.3 | Equipment Failure | Pump Breakdown | RIH (Run In Hole) | Jun-2024 | 6
2024-06-30 | Sagar Prabha | D-11-HH | Halliburton | 10.5 | Equipment Failure | Rotary Table Failure | Drilling 26" | Jun-2024 | 6
2024-06-30 | Sagar Kiran | F-2-HH | ONGC (Own) | 3.6 | HR/Crew | Shift Handover Delay | Completion | Jun-2024 | 6

## Data_Dictionary
DATA DICTIONARY — ONGC NPT Dataset
Every column in the NPT_Data sheet — purpose, type, accepted values, and example
Column | Data Type | Description | Accepted Values / Format | Example
date | Date | Date on which the NPT event occurred | YYYY-MM-DD (stored as Excel date) | 2024-03-15
rig_name | Text | Name of the offshore drilling rig | Sagar Bhushan ¦ Sagar Vijay ¦ Sagar Prabha ¦ Sagar Sampada ¦ Sagar Kiran ¦ Sagar Ekta | Sagar Bhushan
well_name | Text | Identifier of the well being drilled when NPT occurred | Free text — ONGC well naming convention | B-12-HH
contractor | Text | Service contractor responsible for the equipment/operation that caused NPT | Halliburton ¦ Schlumberger ¦ Baker Hughes ¦ ONGC (Own) | Halliburton
npt_hours | Number | Duration of non-productive time for this event (decimal hours) | Positive float, 0.1 – 96.0 | 4.5
cause_category | Text | Top-level classification of NPT root cause | Equipment Failure ¦ Formation/Geological ¦ Weather/Environment ¦ HR/Crew ¦ Logistics/Supply ¦ Well Control ¦ Third Party/Regulatory | Equipment Failure
cause_detail | Text | Specific sub-cause within the category | Free text — see reference list on Cause_Reference sheet | BHA Failure
phase | Text | Drilling phase during which the NPT event occurred | Drilling 26" ¦ Drilling 12.25" ¦ Drilling 8.5" ¦ Running Casing ¦ Cementing ¦ Completion ¦ Running BHA ¦ POOH ¦ RIH ¦ Wellbore Survey ¦ Testing | Drilling 12.25"
month | Text | Formatted month label (derived from date) — for grouping charts | MMM-YYYY format | Mar-2024
month_num | Integer | Month number 1–6 (derived from date) — for sorting trend charts correctly | 1 = January, 2 = February, … 6 = June | 3

## Cause_Reference
NPT CAUSE REFERENCE — Categories, Details & Typical Duration
Reference for workshop — when generating or reviewing NPT data, all cause_detail values should map to one of these categories
Cause Category | Cause Detail | Typical Duration Range | Primary Responsible Party
Equipment Failure | BHA Failure | 2 – 18 hours | Service Contractor / Rig Contractor
Top Drive Malfunction
Pump Breakdown
MWD/LWD Failure
Casing Tong Failure
Drawworks Issue
Rotary Table Failure
Generator Breakdown
BOP Leak
Hook/Block Failure
Formation/Geological | Stuck Pipe | 3 – 24 hours | ONGC Subsurface Team
Lost Circulation
Wellbore Instability
H2S Influx
Kick/Well Control Event
Formation Damage
Tight Hole
Wash-Out
Weather/Environment | High Wind Speed (>25 knots) | 4 – 72 hours | Metocean / Operations
Heavy Swell (>3m)
Low Visibility/Fog
Lightning Stand-Down
Monsoon Operations Halt
Cyclone Warning Stand-Down
HR/Crew | Crew Change Delay | 1 – 8 hours | HR / Contractor HR
Crew Shortage
HSE Training Stand-Down
Crew Sickness
Shift Handover Delay
Competency Issue
Logistics/Supply | Drill Bit Delivery Delay | 2 – 36 hours | Supply Chain / Contractor
Casing Delivery Delay
Chemical Supply Delay
Completion Equipment Delay
Vessel Non-Availability
Cement Shortage
Well Control | BOP Test Failure | 4 – 48 hours | ONGC Well Control Team
Kick Observation & Shut-In
Flow Check
Well Kill Operation
Barrier Integrity Test
Third Party/Regulatory | DGMS Inspection | 1 – 12 hours | Regulatory / DGMS
Environmental Audit
Third Party Certification
Coast Guard Inspection
Waiting on Regulatory Approval

## Summary_Stats
SUMMARY STATISTICS — ONGC NPT Dataset · Jan–Jun 2024
Pre-calculated summaries to validate your Streamlit dashboard output during the workshop
A. OVERALL KPIs
Total NPT Events | Total NPT Hours | Avg NPT per Event (hrs) | Date Range
545 | 8984.9 | 16.5 | Jan–Jun 2024
B. NPT BY CAUSE CATEGORY (use for Pareto chart validation)
Cause Category | Event Count | Total NPT Hours | % of Total NPT
Weather/Environment | 83 | 3337.4 | 37.1%
Equipment Failure | 188 | 2003.5 | 22.3%
Formation/Geological | 111 | 1568.9 | 17.5%
Well Control | 25 | 808.3 | 9.0%
Logistics/Supply | 39 | 752.7 | 8.4%
HR/Crew | 91 | 460 | 5.1%
Third Party/Regulatory | 8 | 54.1 | 0.6%
TOTAL | 545 | 8984.9 | 100.0%
C. NPT BY RIG (use for rig comparison KPI cards)
Rig Name | Events | Total NPT Hrs | Avg per Event | Top Cause
Sagar Bhushan | 121 | 2276.3 | 18.8 | Equipment Failure
Sagar Prabha | 101 | 1802.9 | 17.9 | Weather/Environment
Sagar Kiran | 120 | 1756.7 | 14.6 | Weather/Environment
Sagar Ekta | 81 | 1291.8 | 15.9 | Logistics/Supply
Sagar Sampada | 55 | 1046.6 | 19 | Weather/Environment
Sagar Vijay | 67 | 810.6 | 12.1 | Formation/Geological
D. NPT BY MONTH (use for monthly trend chart validation)
Month | Events | Total NPT Hours | Month-on-Month Change
Jan-2024 | 89 | 1356.2 | —
Feb-2024 | 66 | 815.1 | -39.9%
Mar-2024 | 91 | 1624.4 | +99.3%
Apr-2024 | 94 | 1396.8 | -14.0%
May-2024 | 87 | 1175.7 | -15.8%
Jun-2024 | 118 | 2616.7 | +122.6%

## Workshop_Guide
NINE-STEP HANDS-ON WORKSHOP GUIDE
ONGC NPT Intelligence Dashboard · SDLC & Vibe Coding Masterclass · Facilitator: Satish Medapati
Step | Phase | Title | What You Do | Commands / Prompts | Expected Output
1 | SDLC — Planning & Requirements | Write the PRD | Before any code: write the Product Requirements Document. • Business problem statement • Success metric (measurable) • User story • Acceptance criteria • Data schema • Out of scope | No code needed. Open a new text file: PRD.md Write in plain English: — 'As a Drilling Engineer, I want to see NPT ranked by cause so I can identify the top contributor in < 10 seconds.' — 'Dashboard must not crash when no data matches the filter.' — Data schema: date ¦ rig_name ¦ well_name ¦ contractor ¦ npt_hours ¦ cause_category ¦ cause_detail ¦ phase | PRD.md file saved in project folder. This is the contract. Everything built in Steps 3–9 must satisfy it.
2 | SDLC — Architecture & Design | Create Project Structure | Set up the file and folder structure before writing any code. Deliberate structure = professional project, not a script dumped on a desktop. | Open VS Code Terminal (Ctrl + `): mkdir ongc-npt-dashboard cd ongc-npt-dashboard mkdir data Create empty files: app.py generate_data.py test_app.py requirements.txt README.md Place npt_data.csv inside the data/ folder. | ongc-npt-dashboard/ ├── app.py ├── generate_data.py ├── test_app.py ├── requirements.txt ├── README.md └── data/ └── npt_data.csv
3 | Version Control — git init | Initialise Git Repository | Before writing a single line of application code — initialise version control. Rule: Git first. Always. | In VS Code Terminal: git init git config --global user.name "Your Name" git config --global user.email "you@ongc.co.in" Create .gitignore: __pycache__/ .env *.pyc .DS_Store git add .gitignore README.md requirements.txt git commit -m "chore: initialise project structure and git" | • .git folder visible in VS Code Explorer • First commit in GitLens history panel • VS Code Source Control icon shows 0 changes pending
4 | Vibe Coding — AI Code Generation | Specify to AI → Generate app.py | Open Continue.dev sidebar in VS Code. Write a structured specification prompt — NOT 'build me a dashboard'. Include: data schema, layout requirements, ONGC colors, acceptance criteria. | Paste this into Continue.dev chat: 'Write a Streamlit app in Python called app.py that: 1. Loads data/npt_data.csv with columns: date, rig_name, well_name, contractor, npt_hours, cause_category, cause_detail, phase 2. Sidebar: multiselect for rig_name and cause_category + date range slider 3. Top row: 3 KPI metric cards — Total NPT Hours, Worst Rig (highest NPT), Top Cause Category 4. Pareto bar chart: top 10 causes by total npt_hours (Plotly Express, horizontal) 5. Line chart: monthly total npt_hours per rig (Plotly Express, one line per rig) 6. Raw data table at bottom 7. st.set_page_config(layout="wide", page_title="ONGC NPT Intelligence") 8. Handle empty filter gracefully: if len(df)==0 show st.warning, don't crash 9. ONGC navy background: page_bg_color=#0B2244 (set via st.markdown CSS) Use plotly_chart with use_container_width=True throughout' | app.py generated (~120 lines). Review every section before running: ✓ Correct column names? ✓ Error handling present? ✓ Correct chart types?
5 | SDLC — Development + Testing | Run Locally + Fix Defects | Run the generated app. Test every feature against the acceptance criteria in your PRD. When errors appear — paste to AI and iterate. | In requirements.txt, write: streamlit>=1.32.0 plotly>=5.18.0 pandas>=2.1.0 Install: pip install -r requirements.txt Run app: streamlit run app.py App opens at http://localhost:8501 Test checklist: □ Do all three KPI cards show? □ Does rig_name multiselect filter the charts? □ Does selecting 0 results show a warning (not crash)? □ Does Pareto show top 10 sorted descending? □ Does line chart show 6 distinct rig lines? □ Verify KPI total against Summary_Stats sheet | ✓ App runs in browser ✓ All acceptance criteria met ✓ No crashes on edge cases Expected Total NPT Hours: matches Summary_Stats sheet value
6 | AI-Assisted QA — Code Review | AI Reviews Its Own Code | Ask AI to review the code it generated. Human decides which fixes to accept — not all AI suggestions are correct. | In Continue.dev chat (with app.py open): 'Review this Streamlit app for: 1. Crashes — what if data/npt_data.csv is missing? 2. Performance — what happens with 50,000 rows? 3. Edge cases — what if all filter combinations return 0 rows? 4. Code quality — any logic repeated more than twice that should be a function? 5. Data type — is the date column parsed as datetime, not string? For each issue: show the problem code and your suggested fix.' | AI returns 3–5 findings. Typical fixes: • try/except around pd.read_csv() • @st.cache_data decorator on load function • parse_dates=['date'] in read_csv() • if len(filtered_df) == 0: st.warning() check Apply 2–3 fixes. Re-run. Confirm still works.
7 | SDLC — Testing & QA Automation | Generate + Run Automated Tests | Ask AI to generate a pytest test suite for the app. Run tests. If any fail — fix the app (or the test) and re-run. Target: all tests green before Git commit. | In Continue.dev: 'Write pytest unit tests for app.py in test_app.py covering: 1. data_loads_correctly — does read_csv return a DataFrame with correct columns? 2. total_npt_sum_correct — does groupby sum match expected total? 3. rig_filter_works — filtering to one rig returns only that rig's rows 4. empty_filter_handled — when df is empty, no AttributeError is raised 5. date_column_is_datetime — date column dtype is datetime64 6. cause_category_values_valid — all categories in the fixed allowed list Use pytest fixtures for a test DataFrame. Do not import streamlit.' Run tests: pip install pytest pytest test_app.py -v | test_app.py created. Expected output: test_data_loads_correctly PASSED test_total_npt_sum_correct PASSED test_rig_filter_works PASSED test_empty_filter_handled PASSED test_date_column_datetime PASSED test_categories_valid PASSED 6 passed in < 1 second
8 | Version Control — git commit + push | Commit Everything to Git + Push to GitHub | All tests pass. Code reviewed. Now commit and push. One commit per logical change — not 'everything at once'. | Stage and commit in 3 logical commits: # Commit 1: core app git add app.py git commit -m "feat: add NPT dashboard with pareto and trend charts" # Commit 2: tests git add test_app.py git commit -m "test: add pytest suite — 6 tests all passing" # Commit 3: data and config git add data/npt_data.csv requirements.txt README.md git commit -m "chore: add dataset, requirements and README" # Push to GitHub git remote add origin https://github.com/YOUR_USER/ongc-npt-dashboard.git git push -u origin main # View in VS Code Open GitLens panel → see all 4 commits in history | ✓ GitHub repo shows 4 commits ✓ All files visible in GitHub web UI ✓ Commit history shows who, what, when ✓ GitLens inline blame shows which commit added each line
9 | CI/CD — Deploy to Streamlit Cloud | Deploy to Live URL + Demonstrate CI/CD Loop | Deploy to Streamlit Community Cloud. Then demonstrate the CI/CD loop: make a change → push → app auto-updates. | DEPLOY: 1. Go to share.streamlit.io 2. Sign in with GitHub account 3. Click 'New app' 4. Repository: ongc-npt-dashboard Branch: main ¦ Main file: app.py 5. Click Deploy 6. Wait ~60 seconds 7. Copy the live URL CI/CD DEMO (show the loop): # Make a visible change: # In app.py: change page_title to 'ONGC NPT Dashboard v1.1' git add app.py git commit -m "feat: update page title to v1.1" git push # Watch Streamlit Cloud auto-detect the push # Refresh the URL — change appears in ~45 seconds # Open on phone — confirm it works on mobile | ✓ Live public URL: https://YOUR_APP.streamlit.app ✓ DGM can open on phone without any login ✓ v1.1 title change visible after push ✓ Full SDLC demonstrated: PRD → Code → Review → Tests → Git → Deploy

## Rig_Profiles
RIG PROFILES — Background Context for NPT Dataset
Synthetic rig profiles — for context during the workshop. Not real ONGC operational data.
Rig Name | Type | Location | Primary Contractor | Total NPT Hrs (Jan–Jun 2024) | Top NPT Cause | Notes
Sagar Bhushan | Semi-Submersible | Mumbai High North | Halliburton | 2276.3 | Equipment Failure | Highest NPT — Equipment failures account for 42% of NPT hours. BHA failures are the top single cause.
Sagar Vijay | Jack-Up | Mumbai High South | Schlumberger | 810.6 | Formation/Geological | Second lowest NPT. Formation challenges drive NPT — tight hole and lost circulation in 12.25" section.
Sagar Prabha | Semi-Submersible | Heera Asset | Baker Hughes | 1802.9 | Weather/Environment | Moderate NPT. Mix of equipment and formation issues. Monsoon impact significant in June.
Sagar Sampada | Drill Ship | KG Basin | ONGC (Own) | 1046.6 | Weather/Environment | Lowest NPT overall. Good equipment reliability. Weather NPT elevated due to Bay of Bengal cyclone risk.
Sagar Kiran | Jack-Up | Bassein Field | Halliburton | 1756.7 | Weather/Environment | HR/crew-related NPT is above fleet average — crew change logistics from Bassein location.
Sagar Ekta | Semi-Submersible | Mumbai High East | Schlumberger | 1291.8 | Logistics/Supply | Logistics/supply delays notable — cement and completion equipment delays on 2 wells.